## Stats - KT
Count of KnowTrans | KnowTrans
Stream | Not Started | Completed | Cancelled | WIP | Grand Total | % Completed or Cancelled |  | Required | % Completed | % in WIP | % Not Started
FI | 71 | 141 | 20 |  | 232 | #DIV/0! | DM | 0 | #DIV/0! | #DIV/0! | #DIV/0!
MM | 16 | 42 |  |  | 58 | #DIV/0! | FI | 0 | #DIV/0! | #DIV/0! | #DIV/0!
PP | 1 | 11 |  | 17 | 29 | #DIV/0! | MM | -17 | 0% | -64.71% | -5.882%
QM | 36 |  |  | 11 | 47 | #DIV/0! | MM - ESM | -11
SD | 59 | 22 |  |  | 81 | #DIV/0! | PM | 0 | #DIV/0! | #DIV/0! | #DIV/0!
WM | 12 | 8 |  | 1 | 21 | #DIV/0! | PP | -1 | 0% | -800% | -1200%
Grand Total | 195 | 224 | 20 | 29 | 468 | #DIV/0! | PS | -29 | -68.97% | -772.4% | -672.4%
[6 empty] | #DIV/0! | PS/CPM | 0 | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | #DIV/0! | QM | 0 | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | #DIV/0! | SD | 0 | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | #DIV/0! | SM | 0 | #DIV/0! | #DIV/0! | #DIV/0!
[6 empty] | #DIV/0! | ECM | 0 | #DIV/0! | #DIV/0! | #DIV/0!
[7 empty] | Blank | 0 | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | 0 | #DIV/0! | #DIV/0! | #DIV/0!
Stream | (All)
Test Script Status
1. Not Started
Grand Total
Note on O4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Grand Total - Cancelled
Note on R4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not Started + Blank

## Master List
Stream | Count | Design Document Process | Building Block | Building Block Description | Sub- Process | transxn Ref | Step | customer | Business Resource (Primary user who needs access) | Business Access (Additional users who needs access) | T-code | Fiori | Type | SAP Role | Logical Component | Node Type | Relevant | Config Status | Sprint | Playback 1 Scenarios | Config Resp | KnowTrans | KT Target Date (plan to complete by) | KT Actual Date | KT Resp | KT receivers | KT Notes | BPP Resp | ref BPP | Test Script ID | Test Script Status | Test Script Target Date | Test Script Actual Complete Date | Test Script Resp
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Days Payables Outstanding | Jasleen | Milan, Wendy, Jen, Scott |  | Days Payable Outstanding - Indirect Method (F2895) | CashDiscountForecastKPI | SAP_BR_AP_MANAGER |  |  |  | 9. CANCELLED/Out Of Scope | 5 |  | Gil | Cancelled | 2023-01-27 | 2023-01-27 | Gil
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Print or email payment advice | Jasleen | Milan, Jen |  | Manage Automatic Payments - Scheduling (F0770) | AutomaticPayment | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 5 |  | Gil | Completed | 2023-01-27 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Create Positive Pay File | Jasleen | Milan, Jen, Wendy |  | Create Positive Pay Files - FCHX (FCHX) |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 9. CANCELLED/Out Of Scope | 5 |  | Gil | Cancelled | 2023-01-27 | 2023-01-27 | Gil
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Reprocess Bank Statement Items (F1520) | Eva | Milan, Jen |  | Reprocess Bank Statement Items (F1520) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 1. Not Started | 5 |  | Gil | On-Hold | 2023-01-27 | 2023-01-27 | Gil
FI | 1 | Asset Accounting | 2QY | AA - Reporting | Reporting |  |  | Asset Accounting Overview (F3096) | Colin | Milan, Jen, Wendy |  | Asset Accounting Overview (F3096) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-18 | Gil | Jennifer
FI | 1 | Asset Accounting | BFH | AA - Monthly Processing | Monthly Processing |  |  | Execute Settlement - For AuC (AIBU) | Colin | Milan, Jen | (AIBU) | Execute Settlement - For AuC (AIBU) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Cancelled | 2023-01-13 | 2023-01-27 | Gil
FI | 1 | Asset Accounting | BFH | AA - Daily Processing | Daily Processing |  |  | Asset Acquisition without Order (Integrated AP) | Jasleen | Colin, Milan, Jen | F-90 | Post Acquisition (Integrated AP) - Without Purchase Order (F-90) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | BFH, 1GF | AA - Monthly Processing | Monthly Processing |  |  | Define Distribution Rules - For AuC | Colin | Milan, Jen | AIAB | Define Distribution Rules - For AuC (AIAB) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Cancelled | 2023-01-13 | 2023-01-27 | Gil
FI | 1 | Asset Accounting | J62 | AA - Reporting | Reporting |  |  | Depreciation Reporting | Colin | Milan, Jen, Wendy |  | Depreciation Lists (F1616) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-18 | Gil | Jennifer
FI | 1 | Asset Accounting | J62 | AA - Monthly Processing | Monthly Processing |  |  | Year End Closing | Colin | Milan, Jen |  | Make Company Code Settings - Asset Accounting-Specific (FAA_CMP) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Cancelled | 2023-01-13 | 2023-01-27 | Gil
FI | 1 | Asset Accounting | J62 | AA - Monthly Processing | Monthly Processing |  |  | Undo Year-End Close for Company Code | Colin | Milan, Jen |  | Make Company Code Settings - Asset Accounting-Specific (FAA_CMP) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Cancelled | 2023-01-13 | 2023-01-27 | Gil
FI | 1 | Asset Accounting | J62 | AA - Reporting | Reporting |  |  | Asset Balances | Colin | Milan, Jen, Wendy |  | Asset Balances (F1035) | ApplicationJob | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-18 | Gil | Jennifer
FI | 1 | Asset Accounting | J62 | AA - Reporting | Reporting |  |  | Asset History Sheet | Colin | Milan, Jen, Wendy | AR02 | Asset History Sheet (F1035) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-18 | Gil | Jennifer
FI | 1 | Asset Accounting | J62 | AA - Reporting | Reporting |  |  | Asset Transaction List | Colin | Milan, Jen, Wendy |  | Asset Transactions (F1614) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-18 | Gil | Jennifer
FI | 1 | Asset Accounting | J62 | AA - Reporting | Reporting |  |  | Asset Values | Colin | Milan, Jen, Wendy |  | Display Asset Master Worklist (F1592) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62 | AA - Daily Processing | Daily Processing |  |  | Create Supplier Invoice - Advanced (MIRO) | Jasleen | Colin, Milan, Jen |  | Create Supplier Invoice - Advanced (MIRO) |  | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62 | AA - Daily Processing | Daily Processing |  |  | Asset Sale with Invoice (Integrated) | Colin | Milan, Jen | F-92 | Asset Sale with Invoice |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-11 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62 | AA - Daily Processing | Daily Processing |  |  | Asset sale without Customer (Non-Integrated) | Colin | Milan, Jen | ABAON | Post Asset Sale - Without Customer |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62 | AA - Daily Processing | Daily Processing |  |  | Post Acquisition with Automatic Offsetting Entry (Non-Integrated) | Colin | Milan, Jen | ABZOL | Post Acquisition with Automatic Offsetting Entry |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62 | AA - Master Data | Master Data |  |  | Changes to Asset Master Record | Colin | Milan, Jen | S_ALR_87012037 | Changes to Asset Master Records |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Cancelled | 2023-01-13 | 2023-01-27 | Gil
FI | 1 | Asset Accounting | J62 | AA - Master Data | Master Data |  |  | Delete Asset | Colin | Milan, Jen | AS06 | Delete Asset |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62 | AA - Master Data | Master Data |  |  | Display Asset Master | Colin | Milan, Jen, Wendy | AS03 | Display Asset |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62 | AA - Daily Processing | Daily Processing |  |  | Post Credit Memo After Year of Invoice | Colin | Milan, Jen |  | Post Credit Memo - After Year of Invoice (ABGFL) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 | NEW | Gil | Completed | 2023-01-24 | 2023-01-23 | Gil | Jen
FI | 1 | Asset Accounting | J62 | AA - Daily Processing | Daily Processing |  |  | Post Retirement (Integrated AR) with Customer | Colin | Milan, Jen |  | Post Retirement (Integrated AR) - With Customer (F-92) |  | AP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 | NEW | Gil | Completed | 2023-01-24 | 2023-01-23 | Gil | Jen
FI | 1 | Asset Accounting | J62 | AA - Daily Processing | Daily Processing |  |  | Reverse Journal Entry (Asset Accounting-Specific) | Colin | Milan, Jen |  | Reverse Journal Entry - Asset Accounting-Specific (AB08) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 | NEW | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62 | AA - Monthly Processing | Monthly Processing |  |  | Manage Depreciation Run | Colin | Milan, Jen |  | Schedule Asset Accounting Jobs (F1914) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 | NEW | Gil | Completed |  | 2023-01-18 | Gil | Jennifer
FI | 1 | Asset Accounting | J62, 1GB | AA - Monthly Processing | Monthly Processing |  |  | Manage Depreciation Run | Colin | Milan, Jen |  | Application Job (F1339, F1240, F1478,F1240, F1478, F1483, F2203, F1119, F1297, F1376, F1482, F1484, F1483, F2203, F1119, F1297, F1376, F1485, F1510, F1518, F1519, F1683, F1702, F1719, F1782, F1829, F1914, F1997, F2047, F2228, F2259) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-18 | Gil | Jennifer
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Asset Unplanned Depreciation | Colin | Milan, Jen | ABAAL | Asset Unplanned Depreciation |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-11 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Credit Memo in Year | Colin | Milan, Jen | ABGL | Post Credit Memo - In Year of Invoice | FixedAsset | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-11 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Credit Memo previous Year | Colin | Milan, Jen | ABGF | Post Credit Memo - In Previous Year |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-11 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Post Transfer Within Company Code | Colin | Milan, Jen | ABUMN | Post Transfer - Within Company Code (ABUMN) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-11 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Post Post-Capitalization | Colin | Milan, Jen | ABNAN | Post Post-Capitalization |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-24 | 2023-01-23 | Gil | Jen
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Retirement Due to Scrapping | Colin | Milan, Jen | ABAVN | Post Asset Retirement by Scrapping |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-11 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Post Retirement (Non-Integrated) - Without Customer (ABAON) | Colin | Milan, Jen | ABAON | Post Retirement (Non-Integrated) - Without Customer (ABAON) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-11 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Reverse Line Items | Colin | Milan, Jen | AB08 | Reverse Line Items |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, 1GB | AA - Daily Processing | Daily Processing |  |  | Write-ups | Colin | Milan, Jen | ABZUL | Post Writeup (ABZU) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-24 | 2023-01-23 | Gil | Jen
FI | 1 | Asset Accounting | J62, BFH | AA - Master Data | Master Data |  |  | Display Asset Master Worklist | Colin | Milan, Jen, Wendy |  | Display Asset Master Worklist (F1592) | ApplicationJob | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, BFH | AA - Master Data | Master Data |  |  | Block Asset | Colin | Milan, Jen | AS05 | Block Asset |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, BFH | AA - Master Data | Master Data |  |  | Change Asset Master | Colin | Milan, Jen | AS02 | Change Asset | FixedAsset | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Asset Accounting | J62, BFH | AA - Master Data | Master Data |  |  | Create Asset Master | Colin | Milan, Jen | AS01 | Create Asset |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-13 | 2023-01-10 | Gil | Jen, Wendy
FI | 1 | Bank Accounting & Cash Operations | 16R | Bank Statement - EBS | Bank Statement |  |  | Manage Bank Statements | Eva, Colin | Milan, Jen, Wendy |  | Manage Bank Statements (F1564) | BankStatement | SAP_BR_CASH_SPECIALIST |  |  |  | 1. Not Started | 5 |  | Gil | Not Started | 2023-01-27
FI | 1 | Bank Accounting & Cash Operations | 1EG | Bank Accounting - EBS | Bank Statement |  |  | Import Electronic Bank Statement | Colin | Milan, Jen, Wendy |  | Manage Incoming Payment Files (F1680) | IncomingPaymentFile | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 5 |  | Gil | Not Started | 2023-01-27
FI | 1 | Bank Accounting & Cash Operations | 1EG | AP - Outgoing Payment | AP Payments |  |  | Download File | Milan | Wendy, Jen |  | Manage Payment Media (F1868) | AutomaticPayment | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 5 |  | Gil | Completed | 2023-01-27 | 2023-01-23 | Gil | Jen
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | View Payment List | Jasleen | Milan, Jen, Wendy |  | Display Payment Lists (S_P99_41000099) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 9. CANCELLED/Out Of Scope | 1 |  | Gil | Cancelled | 2022-12-02 | 2022-12-02 | Gil
FI | 1 | Bank Accounting & Cash Operations | 1GO | Bank Accounting - Daily processes | Daily Processing |  |  | Post Cash Journal Entries | Eva | Milan, Jen |  | Post Cash Journal Entries (FBCJ) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-13
FI | 1 | Bank Accounting & Cash Operations |  | Bank Statement - EBS | Bank Statement |  |  | Reprocess Bank Statement Items | Eva | Milan, Jen |  | Reprocess Bank Statement Items |  | SAP_BR_CASH_SPECIALIST |  |  |  | 1. Not Started | 5 |  | Gil | Not Started | 2023-01-27
FI | 1 | Bank Accounting & Cash Operations | BFB | Bank Accounting - Reporting | Reporting |  |  | Cash Flow Analyser | Milan | Wendy, Jen, Scott |  | Cash Flow Analyser (F2332) | Bank | SAP_BR_CASH_SPECIALIST |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-13
FI | 1 | Bank Accounting & Cash Operations | BFB | Bank Statement - EBS | Bank Statement |  |  | Bank Account Balance Reconciliation | Colin | Milan, Jen, Wendy | FCLM_BANK_RECONCIL | Bank Account Balance |  | SAP_BR_CASH_SPECIALIST |  |  |  | 1. Not Started | 5 |  | Gil | Not Started | 2023-01-27
FI | 1 | Bank Accounting & Cash Operations | J78 | Bank Statement - EBS | Bank Statement |  |  | Bank Statement Monitor (Smart Business) | Eva, Colin | Milan, Jen, Wendy |  | Bank Statement Monitor - Bank Account (F1734) | BankAccount | SAP_BR_CASH_MANAGER |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-13
FI | 1 | Bank Accounting & Cash Operations | 1GO | Bank Accounting - Daily processes | Daily Processing |  |  | Display Cash Journal Entries | Eva | Milan, Jen |  | Cash Journal | Bank | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-13
FI | 1 | FI Month End | 2QL | GL - Month end Processing | Monthly Processing |  |  | Manage Allocations (F3338) | Colin | Milan, Jen |  | Manage Allocations (F3338) |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | FI Month End | 1GA | GL - Report | Reporting |  |  | Cash Flow Statement | Milan | Wendy, Jen, Scott |  | Cash Flow Statement - Indirect Method |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 5 |  | Gil | Cancelled | 2023-01-27
FI | 1 | FI Month End | 2QL | GL - Month end Processing | Monthly Processing |  |  | Run Allocations (F3548) | Colin | Milan, Jen |  | Run Allocations (F3548) |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | On-Hold | 2023-01-06 | 2023-01-06 | Gil
FI | 1 | FI Month End | 2QL | GL - Month end Processing | Monthly Processing |  |  | Import Financial Plan Data (F1711) | Jackie, Cristalyne, and AG | Jackie, Cristalyne, and AG |  | Import Financial Plan Data (F1711) |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | FI Month End | BEI | GL - Month end Processing | Monthly Processing |  |  | Release Blocked Invoices | Jasleen | Colin, Milan, Jen | MRBR | Release Blocked Invoices (MRBR) |  | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  |  |  | 1. Not Started | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-23 | Gil | Jen
FI | 1 | FI Month End | BEI | GL - Month end Processing | Monthly Processing |  |  | Run Overhead Calculation - Actual | Colin | Milan, Jen | CO43 | Run Overhead Calculation - Actual (CO43) |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | FI Month End | BEI | GL - Month end Processing | Monthly Processing |  |  | Run Variance Calculation - By Period | Colin | Milan, Jen | KKS5 | Run Variance Calculation - By Period (KKS5) |  | SAP_BR_PRODN_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | FI Month End | BEI | GL - Month end Processing | Monthly Processing |  |  | Analyze Costs by Work Center/Operation (F3331) | Colin, Cristalyne | Milan, Jen |  | Analyze Costs by Work Center/Operation (F3331) |  | SAP_BR_PRODN_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | FI Month End | BEI | GL - Month end Processing | Monthly Processing |  |  | Production Cost Analysis (F1780) | Colin, Cristalyne | Milan, Jen |  | Production Cost Analysis (F1780) |  | SAP_BR_PRODN_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | FI Month End | BEI | GL - Month end Processing | Monthly Processing |  |  | Change Production Order | Colin | Milan, Jen | CO02 | Manage Production Orders |  | SAP_BR_PRODN_SUPERVISOR_DISC |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-06
FI | 1 | FI Month End | 2QL | GL - Month end Processing | Monthly Processing |  |  | Manage Global Accounting Hierarchies (F2918) | Milan | Wendy, Jen |  | Manage Global Accounting Hierarchies (F2918) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | On-Hold | 2023-01-06 | 2023-01-06 | Gil
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Display Tax Information per Country | Colin | Milan, Jen | S_ALR_87012365 | Display Tax Information Per Country |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-06
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Perform Foreign Currency Valuation | Colin | Milan, Jen | FAGL_FCV | Perform Foreign Currency Valuation | RecurringAccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-04 | Gil | Wendy, Jen
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Post Currency Adjustments | Colin | Milan, Jen |  | Post Currency Adjustments (F1606) | FiscalPeriod | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-04 | Gil | Wendy, Jen
MM | 1 | Purchasing Reporting | 1JI | Real-Time Reporting and Monitoring for Procurement | Reporting |  |  | Material Price Variance Analytics List Page | Karmen/ - Chris/Jackson, FPA | Peter, Paul, Colin, Milan, Jen, Wendy |  | Material Price Variance (F3294) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Purchasing Reporting | 1JI | Real-Time Reporting and Monitoring for Procurement | Reporting |  |  | Overdue Purchase Order Items | Karmen/ - Chris/Jackson | Peter, Paul |  | Overdue Purchase Order Items (F0343) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Purchasing Reporting | 1JI | Real-Time Reporting and Monitoring for Procurement | Reporting |  |  | Procurement Overview Page | Karmen/ - Chris/Jackson | Peter, Paul |  | Procurement Overview (F1990) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 3 |  | Daniel CK | Not Started |  |  | Daniel CK
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Post Tax Payable | Colin | Milan, Jen |  | Post Tax Payable (F1597) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-06
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Repost GR/IR Clearing | Jasleen | Milan, Jen | F.19 | Repost GR/IR Clearing | AccountingDocument | SAP_BR_APR_ACCOUNTANT_FICA |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-06
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Regroup Receivables/Payables | Jasleen, Eva | Milan, Jen | FAGLF101 | Regroup Receivables/Payables | AccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-06
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Schedule General Ledger Jobs | Colin | Milan, Jen |  | Application Job (F1339, F1240, F1478,F1240, F1478, F1483, F2203, F1119, F1297, F1376, F1482, F1484, F1483, F2203, F1119, F1297, F1376, F1485, F1510, F1518, F1519, F1683, F1702, F1719, F1782, F1829, F1914, F1997, F2047, F2228, F2259) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Cancelled | 2023-01-06 | 2023-01-27 | Gil
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Clear Open Items Automatically | Milan | Jen | F.13 | Clear Open Items Automatically |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-06
FI | 1 | FI Month End | J58 | GL - Report | Reporting |  |  | Display Financial Statement | Milan | Wendy, Jen, Scott |  | Display Financial Statement (F0708) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 9. CANCELLED/Out Of Scope | 3 |  | Gil | Cancelled | 2023-01-06 | 2023-01-04 | Gil
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Maintain Financial Statement Version | Milan | Wendy, Jen | OB58/FSE3 | Manage Financial Statement Versions (OB58) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Display Chart of Accounts | All Finance | All Finance |  | Manage Chart of Accounts (F0763A) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Month end Processing | Monthly Processing |  |  | Import Financial Plan Data | Jackie, Cristalyne, and AG | Jackie, Cristalyne, and AG |  | Import Financial Plan Data (F1711) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 | NEW | Gil | Not Started
FI | 1 | General Ledger | J58 | GL - Month end Processing | Monthly Processing |  |  | Year-to-Date Balances | All Finance | All Finance |  | Year-to-Date Balance (W0177) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 7. QA Approved | 3 | NEW | Gil | Not Started
FI | 1 | General Ledger | J58 | GL - Month end Processing | Monthly Processing |  |  | Balance Carryforward Status | All Finance | All Finance |  | Balance Carryforward Status (F4683) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 | NEW | Gil | Not Started
FI | 1 | Inventory Accounting | 1ZT | Inventory Accounting - Monthly | Monthly Processing |  |  | Manage Material Valuations | Colin | Milan, Jen, Wendy |  | Manage Material Valuations | Create | SAP_BR_PRODMASTER_SPECIALIST |  |  |  | 1. Not Started | 2 |  | Gil | Not Started | 2022-12-16
FI | 1 | Inventory Accounting | 1ZT | Inventory Accounting - Reporting | Reporting |  |  | Material Inventory Values - Balance Summary | Colin | Milan, Jen, Wendy |  | Material Inventory Values - Balance Summary | Report | SAP_BR_PRODMASTER_SPECIALIST |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | Inventory Accounting | BEG | Inventory Accounting - Monthly | Monthly Processing |  |  | Manage Costing Runs - Estimated Costs | Colin | Milan, Jen, Wendy | CK40N | Manage Costing Runs - Estimated Costs | Create | SAP_BR_INVENTORY_ACCOUNTANT |  |  |  | 1. Not Started | 2 |  | Gil | Not Started | 2022-12-16
FI | 1 | Inventory Accounting | BEG | Inventory Accounting - Monthly | Monthly Processing |  |  | Manage Cost Rates - Plan | Milan | Wendy, Jen |  | Manage Cost Rates - Plan | Create | SAP_BR_INVENTORY_ACCOUNTANT |  |  |  | 1. Not Started | 2 |  | Gil | Not Started | 2022-12-16
FI | 1 | Inventory Accounting | BEI | Inventory Accounting - Monthly | Monthly Processing |  |  | Open new MM Period | Milan | Wendy, Jen | MMPV | Close Periods |  | SAP_BR_PRODMASTER_SPECIALIST |  |  |  | 7. QA Approved | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-04 | Gil | Wendy, Jen
FI | 1 | Inventory Accounting | BEI | Inventory Accounting - Monthly | Monthly Processing |  |  | Run Overhead Calculation - Actual | Colin | Milan, Jen, Wendy |  | Run Overhead Calculation - Actual |  | SAP_BR_PRODN_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | Inventory Accounting | BEI | Inventory Accounting - Monthly | Monthly Processing |  |  | Calculate Work in Process | Colin | Milan, Jen, Wendy |  | Calculate Work in Process - Collective |  | SAP_BR_PRODN_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | Inventory Accounting | BEI | Inventory Accounting - Monthly | Monthly Processing |  |  | Run Variance Calculation - By Period | Colin | Milan, Jen, Wendy |  | Run Variance Calculation - By Period |  | SAP_BR_PRODN_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | Inventory Accounting | BEI | Inventory Accounting - Monthly | Monthly Processing |  |  | Settle Orders | Colin | Milan, Jen, Wendy |  | Settle Orders - Optimized |  | SAP_BR_PRODN_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | Inventory Accounting | BEI | Inventory Accounting - Monthly | Monthly Processing |  |  | Release Blocked Invoices | Jasleen | Milan, Jen | MRBR | Release Blocked Invoices |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 1. Not Started | 2 |  | Gil | Completed | 2022-12-16 | 2023-01-23 | Gil | Jen
FI | 1 | Inventory Accounting | BEI | Inventory Accounting - Reporting | Reporting |  |  | Production Cost Analysis | Colin | Milan, Jen, Wendy |  | Production Cost Analysis |  | SAP_BR_PRODN_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | Overhead Cost Accounting | BEV | CO - Daily Processing | Daily Processing |  |  | Analyze Order | Colin | Milan, Jen, Wendy | KKBC_ORD | Analyze Order |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-27 | 2023-01-11 | Gil | Jen
FI | 1 | Overhead Cost Accounting | BEV | CO - Daily Processing | Daily Processing |  |  | Internal Order Actuals | Colin | Milan, Jen, Wendy |  | Internal Orders - Actuals (F0941A) |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-27 | 2023-01-11 | Gil | Jen
FI | 1 | Overhead Cost Accounting | BEV | CO - Daily Processing | Daily Processing |  |  | Create Internal order | Colin, Jasleen | Milan, Jen |  | Manage Internal Orders (F1604) | InternalOrder | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-27 | 2023-01-11 | Gil | Jen
FI | 1 | Overhead Cost Accounting | BEV | CO - Monthly Processing | Monthly Processing |  |  | Create Settlement Rules with Cost Center | Colin | Milan, Jen |  | Manage Internal Orders (F1604) | InternalOrder | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-27 | 2023-01-11 | Gil | Jen
FI | 1 | Overhead Cost Accounting | BEV | CO - Monthly Processing | Monthly Processing |  |  | Executing Settlement Internal Order | Colin | Milan, Jen | KO8GH | Run Actual Settlement Internal Orders |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 3. Baseline Completed | 4 |  | Gil | Completed | 2023-01-27 | 2023-01-11 | Gil | Jen
MM | 1 | Inventory Management | 950 | PSA Replenishment | Goods Receipt |  |  | Posting the Goods Receipt for External Procurement | Karmen/ - Chris/Jackson | Peter, Paul | MIGO | Post Goods Movement (MIGO) |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-24 | Daniel CK | Karmen, Louie
MM | 1 | Purchasing - Services | 22Z | Procurement of Services | Procurement of Services |  |  | Check Service Entry Sheet Details(Optional) | Karmen/ - Chris/Jackson | Peter, Paul |  | Manage Service Entry Sheets - Lean Services (F2027) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
FI | 1 | Overhead Cost Accounting | BEV | CO - Monthly Processing | Monthly Processing |  |  | Run Overhead Calculation - Orders | Colin | Milan, Jen |  | Run Overhead Calculation - Orders - Actual | Orders | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-27
FI | 1 | Overhead Cost Accounting | J54 | CO - Monthly Processing | Monthly Processing |  |  | Manage Allocations | Colin | Milan, Jen |  | Manage Allocations |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-27
FI | 1 | Overhead Cost Accounting | J54 | CO - Monthly Processing | Monthly Processing |  |  | Run Allocations | Colin | Milan, Jen |  | Run Allocations (F3548) |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-27
FI | 1 | Overhead Cost Accounting | J54 | CO - Monthly Processing | Monthly Processing |  |  | Allocation Results | Colin | Milan, Jen, Wendy |  | Allocation Results (F4363) |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-27
FI | 1 | Overhead Cost Accounting | J54 | CO - Daily Processing | Daily Processing |  |  | Cost Centers Actual Data Reporting | Colin, Cristalyne | Milan, Jen, Wendy, AG |  | Cost Centers - Actuals |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 2 |  | Gil | Not Started | 2022-12-16
FI | 1 | Overhead Cost Accounting | J54 | CO - Daily Processing | Daily Processing |  |  | Commitments by Cost Center | Colin, Cristalyne | Milan, Jen, Wendy, AG |  | Commitments by Cost Center (F3016) | Cost Center | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 2 |  | Gil | Not Started | 2022-12-16
FI | 1 | Overhead Cost Accounting | J54 | CO - Monthly Processing | Monthly Processing |  |  | Manage Direct Activity Allocation | Colin | Milan, Jen |  | Manage Direct Activity Allocation |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-27
FI | 1 | Overhead Cost Accounting | J54 | CO - Monthly Processing | Monthly Processing |  |  | Import Financial Plan Data - Cost Centers and other Objects | Jackie, Cristalyne, and AG | Jackie, Cristalyne, and AG |  | Import Financial Plan Data | Cost Center | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-27
FI | 1 | Overhead Cost Accounting | J54 | CO - Monthly Processing | Monthly Processing |  |  | Copy Financial Plan Data - Cost Centers and other Objects | Jackie, Cristalyne, and AG | Jackie, Cristalyne, and AG |  | Copy Financial Plan Data | Cost Center | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 1. Not Started | 4 |  | Gil | Not Started | 2023-01-27
FI | 1 | General Ledger | J58 | GL - Month end Processing | Monthly Processing |  |  | Statement of Changes in General Ledger (W0162) | As per Gil, app not required | As per Gil, app not required |  | Statement of Changes in General Ledger (W0162) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 | NEW | Gil | Not Started
FI | 1 | Accounts Payable | J60 | AP - Master Data | AP - Master Data |  |  | Confirm Supplier List (Accounting) | Jasleen | Milan, Jen, Wendy | FK09 | Confirm Supplier List (Accounting) |  | SAP_BR_BUPA_MASTER_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Manage Customer Down Payment Requests (F1689) | Eva | Milan, Jen |  | Manage Customer Down Payment Requests (F1689) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Not Started | 2022-12-09
FI | 1 | Accounts Receivable | J59 | AR - Outgoing Payment | Payments |  |  | Clear Incoming Payments - Manual Clearing (F0773) | Eva | Milan, Jen |  | Clear Incoming Payments - Manual Clearing (F0773) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2023-01-25 |  | Eva, Jen
FI | 1 | Accounts Receivable | J59 | AR - Outgoing Payment | Payments |  |  | Post Incoming Payments (F1345) | Eva | Milan, Jen |  | Post Incoming Payments (F1345) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Not Started | 2022-12-09 | 2022-12-12
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | create customer statement (Create Correspondence) | Eva | Milan, Jen |  | Create Correspondence (F0744A) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Profitability and Cost Analysis | J55 | CO - Reporting | Reporting |  |  | Market Segments Actual Report | Colin, Milan, Jackie, Cristalyne, and AG | Wendy, Jen, Scott |  | Market Segments Actuals |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 1. Not Started | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Create Bank G/L Account | Milan | Jen |  | Manage G/L Account Master Data (F0731A) | GLAccount | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Cancelled | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Credit Management | BD6 | Credit Management | Credit Management |  |  | Mass assignment of the role to the business partner is scheduled. | Eva | Milan, Jen |  | Schedule Credit Management Jobs (F3748) |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Cancelled | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | Credit Management | BD6 | Credit Management | Credit Management |  |  | Manage Business Partner - Credit Profile (UKM_BP) | Eva | Milan, Jen |  | Manage Business Partner - Credit Profile (UKM_BP) |  | SAP_BR_AA_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Update Bank G/L Account | Milan | Jen |  | Manage G/L Account Master Data (F0731A) | GLAccount | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Cancelled | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | 1GA | GL - Daily Processing | Daily Processing |  |  | Manage Teams and Responsibilities (F2412) | Milan | Wendy, Jen |  | Manage Teams and Responsibilities (F2412) |  | SAP_BR_BPC_EXPERT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | 1GA | GL - Daily Processing | Daily Processing |  |  | Manage Workflows for General Journal Entry Verification | Milan | Wendy, Jen |  | Manage Workflows for General Journal Entry Verification (F2720) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | FI Month End | 1GA | GL - Report | Reporting |  |  | Trial Balance | All Finance | All Finance |  | Trial Balance (F0996A) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 1 | Alternative 1: Convert Planned Order to Process Order | Louie/Karmen/Paul | Louie/Karmen/Paul | MD04 | Stock Requirements List (MD04) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 01 09 2023 | 01 09 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  |  | 1. Not Started |  |  | Alex C
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 2 | Alternative 2: Create Process Order | Louie/Karmen/Paul | Louie/Karmen/Paul | COR1 | Create Process Order (COR1) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 3 | Available to Promise | Louie/Karmen/Paul | Louie/Karmen/Paul | COR1 | Create Process Order (COR1) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 01 09 2023 | 01 09 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  |  | 1. Not Started |  |  | Alex C
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 4 | Scheduling | Louie/Karmen/Paul | Louie/Karmen/Paul | COR1 | Create Process Order (COR1) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 5 | Release | Louie/Karmen/Paul | Louie/Karmen/Paul | COR2 | Change Process Order (COR2) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 01 09 2023 | 01 09 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  |  | 1. Not Started |  |  | Alex C
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 6 | Review Batch | Louie/Karmen/Paul | Louie/Karmen/Paul | COR3 | Display Process Order (COR3) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 7 | Print Shop Floor Papers | Louie/Karmen/Paul | Louie/Karmen/Paul | COR3 | Display Process Order (COR3) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 01 09 2023 | 01 09 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  |  | 1. Not Started |  |  | Alex C
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 8 | Materials Staging | Louie/Karmen/Paul | Louie/Karmen/Paul | ? | To be determiend based on the PP-PI/EWM Setup |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 9 | Monitor Order Progress | Louie/Karmen/Paul | Louie/Karmen/Paul | COR3 | Monitor Order Progress |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 10 | Confirming Process Order | Louie/Karmen/Paul | Louie/Karmen/Paul | CO19 | Confirm Production Operation - Time Event |  | SAP_BR_PRODN_SUPERVISOR_PROC |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 11 | Display and Review Process Order Confirmation | Louie/Karmen/Paul | Louie/Karmen/Paul | COR3 | Display Process Order (COR3) |  | SAP_BR_PRODN_SUPERVISOR_PROC |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 12 | Good Receipt | Louie/Karmen/Paul | Louie/Karmen/Paul | ? | To be determiend based on the PP-PI/EWM Setup |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 13 | Technically Complete Process Order | Louie/Karmen/Paul | Louie/Karmen/Paul | COR2 | Change Process Order (COR2) |  | SAP_BR_PRODN_SUPERVISOR_PROC |  |  |  | 3. Baseline Completed | 3 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Make to Stock | 909 | Make-to-Stock (Process Industry) with Staging using PMR in EWM | Make to Stock |  | 14 | Process Order Information System | Louie/Karmen/Paul | Louie/Karmen/Paul | COOISPI | Process Order Information System (COOISPI) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 5 |  | AlexC | Completed | 02 16 2023 | 02 16 2023 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira
PP | 1 | Material Requirements Planning | 2GI | Material Requirements Planning | Material Requirements Planning |  | 1 | Create PIRs | Louie/Karmen/Paul | Louie/Karmen/Paul | N/A | Manage PIRs |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 2 |  | AlexC | Completed | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-002-01 - Material Requirements Planning
PP | 1 | Material Requirements Planning | 2GI | Material Requirements Planning | Material Requirements Planning |  | 2 | Review PIRs | Louie/Karmen/Paul | Louie/Karmen/Paul | N/A | Check Material Coverage |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 2 |  | AlexC | Completed | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-002-01 - Material Requirements Planning
PP | 1 | Material Requirements Planning | 2GI | Material Requirements Planning | Material Requirements Planning |  | 3 | Schedule MRP Runs | Louie/Karmen/Paul | Louie/Karmen/Paul | N/A | Schedule MRP Runs |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 2 |  | AlexC | Completed | 01 09 2023 | 01 25 2023 | AlexC | Karmen Ho |  |  |  | SAP-PP-TS-002-01 - Material Requirements Planning | 1. Not Started |  |  | Alex C
PP | 1 | Material Requirements Planning | 2GI | Material Requirements Planning | Material Requirements Planning |  | 4 | Check Material Coverage | Louie/Karmen/Paul | Louie/Karmen/Paul | N/A | Check Material Coverage |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 2 |  | AlexC | Completed | 01 09 2023 | 01 25 2023 | AlexC | Karmen Ho |  |  |  | SAP-PP-TS-002-01 - Material Requirements Planning | 1. Not Started |  |  | Alex C
PP | 1 | Material Requirements Planning | 2GI | Material Requirements Planning | Material Requirements Planning |  | 5 | Display MRP Run Material Issues (optional) | Louie/Karmen/Paul | Louie/Karmen/Paul | N/A | Display MRP Material Issues |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 2 |  | AlexC | Completed | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-002-01 - Material Requirements Planning
PP | 1 | Material Requirements Planning | 2GI | Material Requirements Planning | Material Requirements Planning |  | 6 | Monitor and Manage Material Shortages | Louie/Karmen/Paul | Louie/Karmen/Paul | N/A | Monitor Material Coverage Net segments |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 2 |  | AlexC | Completed | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-002-01 - Material Requirements Planning
PP | 1 | Material Requirements Planning | 2GI | Material Requirements Planning | Material Requirements Planning |  | 7 | Monitor External Requirements | Louie/Karmen/Paul | Louie/Karmen/Paul |  | Monitor External Requirements |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 5 |  | AlexC | Completed |  | 01 20 2023 | AlexC | Karmen Ho, Louie Teixeira, Scott Alley
PP | 1 | Material Requirements Planning | 2GI | Material Requirements Planning | Material Requirements Planning |  | 8 | Monitor Internal Requirements | Louie/Karmen/Paul | Louie/Karmen/Paul |  | Monitor Internal Requirements |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 5 |  | AlexC | Completed |  | 01 20 2023 | AlexC | Karmen Ho, Louie Teixeira, Scott Alley
FI | 1 | Credit Management | BD6 | Credit Management | Credit Management |  |  | Manage Credit Cases (UKM_CASE) | Eva | Milan, Jen |  | Manage Documented Credit Decisions |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Cancelled | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | FI Month End | 1GA | GL - Report | Reporting |  |  | Trial Balance | All Finance | All Finance |  | Trial Balance Comparison (F2767) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
FI | 1 | Credit Management | BD6 | Credit Management | Credit Management |  |  | Manage Documented Credit Decisions (UKM_MY_DCDS) | Eva | Milan, Jen |  | Manage Documented Credit Decisions |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | Credit Management | BD6 | Credit Management - Reporting | Reporting |  |  | Display Credit Management Log (F2162) | Eva | Milan, Jen, Wendy |  | Display Credit Management Log (F2162) |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Cancelled | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | Credit Management | BD6 | Credit Management - Reporting | Reporting |  |  | Display Credit Master Data (UKM_BP_DISPLAY) | Eva | Milan, Jen, Wendy |  | Display Credit Master Data (UKM_BP_DISPLAY) |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Cancelled | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | FI Month End | 2QL | GL - Report | Reporting |  |  | Profit Centers - Plan/Actual (F2889) | All Finance | All Finance |  | Profit Centers - Plan/Actual (F2889) |  | SAP_BR_DIVISION_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
FI | 1 | FI Month End | 2QL | GL - Report | Reporting |  |  | Cost Centers - Plan/Actual (F0949A | All Finance | All Finance |  | Cost Centers - Plan/Actual (F0949A |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Not Started | 2023-01-27
FI | 1 | Credit Management | BD6 | Credit Management - Reporting | Reporting |  |  | Credit Limit Utilization (S/4HANA) (F1751) | Eva | Milan, Jen, Wendy |  | Credit Limit Utilization (S/4HANA) (F1751) |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Cancelled | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | General Ledger | 1GA | GL - Daily Processing | Daily Processing |  |  | Display Line Item Entry (F2218) | All Finance | All Finance |  | Display Line Item Entry (F2218) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Manage G/L Account Master Data | Milan | Wendy, Jen | FS00 | Manage G/L Account Master Data (F0731A) | ChartOfAccounts | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Manage Profit Centers (F0732) | Milan | Wendy, Jen |  | Manage Profit Centers (F0732) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Credit Management | BD6 | Credit Management - Reporting | Reporting |  |  | Display Credit Data - Segment (UKM_MASS_DSP2) | Eva | Milan, Jen, Wendy |  | Display Credit Account Data |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Not Started | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | Credit Management | BD6 | Credit Management - Reporting | Reporting |  |  | Display Credit Exposure (UKM_COMMITMENTS) | Eva | Milan, Jen, Wendy |  | Display Credit Exposure |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Not Started | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | Credit Management | BD6 | Credit Management - Reporting | Reporting |  |  | Analyze Credit Exposure - By Country (F2541) | Eva | Milan, Jen, Wendy |  | Analyze Credit Exposure - By Country (F2541) |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Not Started | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | Credit Management | BD6 | Credit Management - Reporting | Reporting |  |  | Display Credit Limit Utilization (UKM_MALUS_DSP) | Eva | Milan, Jen, Wendy |  | Credit Limit Utilization |  | SAP_BR_CREDIT_CONTROLLER |  |  |  | 3. Baseline Completed | 2 |  | Gil | Not Started | 2022-12-09 | 2022-12-09 | Gil | Wendy, Jennifer, Eva, Rob K
FI | 1 | Overhead Cost Accounting | J54 | CO - Master data | Master Data |  |  | Manage Cost Centers | Milan | Wendy, Jen |  | Manage Cost Centers |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Pack Outbound Deliveries | Louie | Paul/Peter |  | Pack Outbound Deliveries (F3193) |  | SAP_BR_WAREHOUSE_OPERATIVE_EWM |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Not Started |  |  | Daniel CK
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Analyze Differences | Louie | Paul/Peter | /SCWM/DIFF_ANALYZER | Analyze Differences |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-12-01 | Daniel CK | Karmen, Louie, Paul
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Create Physical Inventory | Louie | Paul/Peter | /SCWM/PI_CREATE | Create Physical Inventory |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-12-01 | Daniel CK | Karmen, Louie, Paul
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Process Physical Inventory | Louie | Paul/Peter | /SCWM/PI_PROCESS | Process Physical Inventory |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-12-01 | Daniel CK | Karmen, Louie, Paul
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Test RF Environment | Louie | Paul/Peter | /SCWM/RFUI | Test RF Environment |  | SAP_BR_WAREHOUSE_OPERATIVE_EWM |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | WIP |  |  | Daniel CK
FI | 1 | Overhead Cost Accounting | J54 | CO - Master data | Master Data |  |  | Manage Cost Center Group | Milan | Wendy, Jen |  | Manage Cost Center Group |  | SAP_BR_OVERHEAD_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Warehouse Monitor | Louie | Paul/Peter | /SCWM/MON | Warehouse Monitor |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-24 | Daniel CK | Karmen, Louie
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Create Inbound Delivery | Louie | Paul/Peter | VL31N | Create Inbound Delivery |  | SAP_BR_RECEIVING_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-24 | Daniel CK | Karmen, Louie
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Display Inbound Delivery | Louie | Paul/Peter | VL33N | Display Inbound Delivery |  | SAP_BR_RECEIVING_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-24 | Daniel CK | Karmen, Louie
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Maintain Inbound Delivery | Louie | Paul/Peter | /SCWM/PRDI | Maintain Inbound Delivery |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-24 | Daniel CK | Karmen, Louie
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Maintain Outbound Delivery Order | Louie | Paul/Peter | /SCWM/PRDO | Maintain Outbound Delivery Order |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2023-01-05 | Daniel CK | Scott, Karmen, Louie, Remo, Bana, Richard
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Make Posting Change for Product | Louie | Paul/Peter | /SCWM/POST | Make Posting Change for Product |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Not Started |  |  | Daniel CK | Karmen, Louie
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Post Unplanned Goods Issue | Louie | Paul/Peter | /SCWM/ADGI | Post Unplanned Goods Issue |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Not Started |  |  | Daniel CK | Karmen, Louie
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Move Product | Louie | Paul/Peter | /SCWM/ADPROD | Move Product |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Not Started |  |  | Daniel CK | Karmen, Louie
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Maintain Resource | Louie | Paul/Peter | /SCWM/RSRC | Maintain Resource |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Maintain Users | Louie | Paul/Peter | /SCWM/USER | Maintain Users |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
FI | 1 | FI Month End | BEI | GL - Month end Processing | Monthly Processing |  |  | Close Periods | Milan | Wendy, Jen | MMPV | Close Periods (MMPV) |  | SAP_BR_PRODMASTER_SPECIALIST |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-04 | Gil | Wendy, Jen
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Create Storage Bin | Louie | Paul/Peter | /SCWM/LS01 | Create Storage Bin |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Edit Storage bin | Louie | Paul/Peter | /SCWM/LS02 | Edit Storage bin |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Display Storage Bin | Louie | Paul/Peter | /SCWM/LS03 | Display Storage Bin |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Manage Profit Center Groups | Milan | Wendy, Jen |  | Manage Profit Center Groups |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Change Bank Account | Milan | Jen |  | Manage Bank Accounts - manage Master Data (F1366) | BankAccount | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Close and Reopen Bank Account | Milan | Jen |  | Manage Bank Accounts - manage Master Data (F1366) | BankAccount | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Mass Edit Storage Bins | Louie | Paul/Peter | /SCWM/LS11 | Mass Change Storage Bins |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Create Bank Account | Milan | Jen |  | Manage Bank Accounts - manage Master Data (F1366) | BankAccount | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Export Bank Account | Milan | Jen |  | Manage Bank Accounts - manage Master Data (F1366) | BankAccount | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Import Bank Account | Milan | Jen |  | Manage Bank Accounts - manage Master Data (F1366) | BankAccount | SAP_BR_CONFIGURATION_EXPERT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Manage Banks | Milan | Wendy, Jen |  | Manage Banks (F1574) | Bank | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Sort Storage Bins | Louie | Paul/Peter | /SCWM/SBST | Sort Storage Bins |  | No standard role, add to SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
WM | 1 | Production and Sell standard products | 54V | Production and Sell standard products | EWM Stock Management |  |  | Assign Bin to PSA/Product | Louie | Paul/Peter | /SCWM/PSASTAGE | Assign Bin to PSA/Product |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 2. WIP | 4 |  | Daniel CK | Not Started |  |  | Daniel CK
FI | 1 | Bank Accounting & Cash Operations | BFA | Bank Accounting - Master Data | Master Data |  |  | Manage House Banks | Milan | Wendy, Jen |  | Manage Banks (F1574) | Bank | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Overhead Cost Accounting | BEV | CO - Daily Processing | Daily Processing |  |  | Enter General Ledger Account Document | Eva, Jasleen, Colin, Jen | Milan |  | Post General Journal Entries (F0718 ) | AccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | BGC | GL - Report | Reporting |  |  | General Ledger Overview | All Finance | All Finance |  | General Ledger Overview (F2445). |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | FI Month End | BGC | GL - Report | Reporting |  |  | Accounts Payable Overview (F2917) | Jasleen | Milan, Wendy, Jen, Scott |  | Accounts Payable Overview (F2917) |  | SAP_BR_AP_MANAGER |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
MM | 1 | Inventory Reporting | BGG | Analytics - Inventory | Reporting |  |  | View Inventory Turnover Analysis | Louie | Peter, Paul |  | Inventory Turnover Analysis (F1956) | analyzeInventoryTurnover | SAP_BR_INVENTORY_MANAGER |  |  | ACTIVE | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Inventory Reporting | BGG | Analytics - Inventory | Reporting |  |  | View Slow or Non-Moving Materials | Louie | Peter, Paul |  | Slow or Non-Moving Materials (F2137) | displaySlowOrNonMoving | SAP_BR_INVENTORY_MANAGER |  |  | ACTIVE | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Stock Transfer Order | 134 | Stock Transfer Order - intra-company | Stock Transfer Order |  |  | Process Purchase Requisitions | Karmen/ - Chris/Jackson, Louie | Peter, Paul |  | Process Purchase Requisitions F1048 | assign | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-25 | Daniel CK | Karmen, Louie
MM | 1 | Inventory Reporting | BGG | SAP Fiori Analytical Apps for Inventory and Warehouse Management | Reporting |  |  | Overview Inventory Management | Karmen/ - Chris/Jackson, Louie | Peter, Paul |  | Overview Inventory Management (F2769) |  | SAP_BR_INVENTORY_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Inventory Reporting | BGG | SAP Fiori Analytical Apps for Inventory and Warehouse Management | Reporting |  |  | Overview Inventory Processing | Karmen/ - Chris/Jackson, Louie | Peter, Paul |  | Overview Inventory Processing (F2416) |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | MM Master Data | BHD | BHD | Purchasing Info Record |  |  | Manage purchasing infor records | Karmen/ - Chris/Jackson | Peter, Paul |  | Manage Purchasing Info Records (F1982) | displayBySupplier | SAP_BR_PURCHASER |  |  | ACTIVE | 3. Baseline Completed | 3 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | MM Master Data | BHD | BHD | Purchasing Info Record |  |  | Display Purchase Info Record | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul | ME13 | Display Purchase Info Record | display | SAP_BR_PURCHASER |  |  | ACTIVE | 3. Baseline Completed | 3 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | MM Master Data | BHD | BHD | Purchasing Info Record |  |  | Change Purchase Info Record | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul | ME12 | Change Purchase Info Record | change | SAP_BR_PURCHASER |  |  | ACTIVE | 3. Baseline Completed | 3 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | MM Master Data | BHD | BHD | Purchasing Info Record |  |  | Creating Purchasing Info Record | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul | ME11 | Creating Purchasing Info Record | create | SAP_BR_PURCHASER |  |  | ACTIVE | 3. Baseline Completed | 3 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
PP | 1 | Production Planning Master Data | PMD | Production Planning Master Data | Master Data |  | 1 | Material Master - MRP | Louie/Karmen/Paul | Louie/Karmen/Paul | MM01 | Create Material (MM01) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 2 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
PP | 1 | Production Planning Master Data | PMD | Production Planning Master Data | Master Data |  | 2 | Material Master - Work Scheduling | Louie/Karmen/Paul | Louie/Karmen/Paul | MM01 | Create Material (MM01) |  | SAP_BR_PRODN_PLNR |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
PP | 1 | Production Planning Master Data | 3X8 | Create Resource | Resource |  | 3 | Create Resource | Louie/Karmen/Paul | Louie/Karmen/Paul | CRC1 | Create Resource (CRC1) |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
PP | 1 | Production Planning Master Data | 3X8 | Create Resource | Resource |  | 4 | Review Resource List | Louie/Karmen/Paul | Louie/Karmen/Paul | CR60 | Work Center List |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
PP | 1 | Production Planning Master Data | 3X9 | Create Master Recipe | Master Data |  | 5 | Create Change Number | Louie/Karmen/Paul | Louie/Karmen/Paul |  | Manage Change Masters |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
PP | 1 | Production Planning Master Data | 3X9 | Create Master Recipe | Master Data |  | 6 | Create Production Version | Louie/Karmen/Paul | Louie/Karmen/Paul | C223 | Manage Production Version (C223) |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
PP | 1 | Production Planning Master Data | 3X9 | Create Master Recipe | Master Data |  | 7 | Create Master Recipe and Bill of Material | Louie/Karmen/Paul | Louie/Karmen/Paul | C201 | Create Master Recipe (C201) |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
PP | 1 | Production Planning Master Data | 3X9 | Create Master Recipe | Master Data |  | 8 | Production Version - Consistency Check | Louie/Karmen/Paul | Louie/Karmen/Paul | C201 | Manage Production Version (C223) |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
PP | 1 | Production Planning Master Data | 3X9 | Create Master Recipe | Master Data |  | 9 | Inactivate Change Number | Louie/Karmen/Paul | Louie/Karmen/Paul |  | Manage Change Masters |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP | 11 30 2022 | 12 08 2022 | AlexC | Paul Stock, Karmen Ho, Louie Teixeira |  |  |  | SAP-PP-TS-001-01 - Production Planning Master Data
FI | 1 | FI Month End | BGC | GL - Report | Reporting |  |  | Accounts Receivable Overview (F3242) | Eva | Milan, Wendy, Jen, Scott |  | Accounts Receivable Overview (F3242) |  | SAP_BR_AR_MANAGER |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
MM | 1 | Purchasing - Inventory | J45 | Procurement of Direct Materials | Purchase Order Down Payment |  |  | Monitor Down Payments (Optional) | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul |  | Monitor Purchase Order Down Payments (F2877) |  | SAP_BR_PURCHASER |  |  |  | 1. Not Started | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 1 | Display Inspection Plan for Inspection Characteristics | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra | QP03 | Display Inspection Plan (QP03) |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 2 | Display Material Stock before Goods Receipt | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 3 | Display Material Stock Before Quality Inspection | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful, Courtney, Esther, Darshand, Mike, Karen | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 4 | Display Quality Technician Overview | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra |  | Quality Technician Overview |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 5 | Display Open Inspection Lots | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful, Courtney, Esther, Darshand, Mike, Karen | Demetra |  | Manage Inspection Lots |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
MM | 1 | Material Master | BLF | Batch Management | Batch Management |  |  | Maintaining Batch Master Record Alternative 1 | Karmen/Louie/Louie | Peter, Paul | MSC1N | Create batch master |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-25 | Daniel CK | Karmen, Louie
MM | 1 | Material Master | BLF | Batch Management | Batch Management |  |  | Maintaining Batch Master Record Alternative 1 | Karmen/Louie/Louie | Peter, Paul | MSC2N | Change batch master |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-25 | Daniel CK | Karmen, Louie
MM | 1 | Material Master | BLF | Batch Management | Batch Management |  |  | Maintaining Batch Master Record Alternative 1 | Karmen/Louie/Louie | Peter, Paul | MSC3N | Display batch master |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-25 | Daniel CK | Karmen, Louie
MM | 1 | Inventory Management | BMC | Core Inventory Management | Stock Management |  |  | Dead Stock Analysis | Karmen/ - Chris/Jackson, Louie | Peter, Paul |  | Dead Stock Analysis (F2899) |  | SAP_BR_INVENTORY_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Inventory Management | BMC | Core Inventory Management | Stock Management |  |  | Goods Movement Analysis | Karmen/ - Chris/Jackson, Louie | Peter, Paul |  | Goods Movement Analysis (F2912) |  | SAP_BR_INVENTORY_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Inventory Management | BMC | Core Inventory Management | Stock Management |  |  | Stock Overview - Single Material | Karmen/ - Chris/Jackson, Louie | Peter, Paul |  | Stock - Single Material (F1076) |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-25 | Daniel CK | Karmen, Louie
MM | 1 | Inventory Management | BMC | Core Inventory Management | Stock Management |  |  | Stock - Multiple materials | Karmen/ - Chris/Jackson, Louie | Peter, Paul |  | Stock - Multiple Mateirals F1595 |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2022-11-24 | Daniel CK | Karmen, Louie
MM | 1 | Inventory Management | BMC | Core Inventory Management | Stock Management |  |  | Stock Overview | Karmen/ - Chris/Jackson, Louie | Peter, Paul | MMBE | Display stock overview |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-25 | Daniel CK | Karmen, Louie
MM | 1 | Inventory Management | BMC | Core Inventory Management | Stock Management |  |  | Display Material Document List | Karmen/ - Chris/Jackson, Louie | Peter, Paul | MB51 | Display Material Document List |  | SAP_BR_WAREHOUSE_CLERK_EWM |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-25 | Daniel CK | Karmen, Louie
MM | 1 | Purchasing - Supplier Returns | BMK | Return to Supplier | Return to Supplier |  |  | Create Return Purchase order with Reference | Louie | Peter, Paul | MIGO | Post Goods Movement (MIGO) |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Completed |  | 2022-12-15 | Daniel CK | Karment, Louie, Richard
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Create Physical Inventory Documents | Louie | Peter, Paul | MI31 | Create PI Documents - Regular Stock (MI31) |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Create Physical Inventory Document (Single Creation, non EWM) | Louie | Peter, Paul | MI01 | Create Single PI Document (MI01) |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Change Physical inventory document | Louie | Peter, Paul | MI02 | Change Physical inventory document |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Display physical inventory document | Louie | Peter, Paul | MI03 | Display physical inventory document |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Enter Inventory Count | Louie | Peter, Paul | MI04 | Enter Inventory Count |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Change Inventory Count | Louie | Peter, Paul | MI05 | Change Inventory Count |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Display Inventory Count | Louie | Peter, Paul | MI06 | Display Inventory Count |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Physical Inventory Document Overview | Louie, Milan | Peter, Paul, Jen |  | Physical Inventory Document Overview (F0379A) |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Print Physical Inventory Documents | Louie, Milan | Peter, Paul, Jen | MI21 | Print Physical Inventory Documents |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | List and post Inventory Count Differences | Louie | Peter, Paul | MI20 | Process Physical Inventory Count Results |  | SAP_BR_INVENTORY_MANAGER |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Recount | Louie | Peter, Paul | MI11 | Request Physical Inventory Recount |  | SAP_BR_INVENTORY_MANAGER |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Inventory Management | BML | Physical Inventory - Inventory Count and Adjustment | Stock Management |  |  | Post inventory difference (individual PID) | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul | MI07 | Post inventory difference |  | SAP_BR_INVENTORY_MANAGER |  |  |  | 3. Baseline Completed | 2 |  | Daniel CK | Completed |  | 2022-11-29 | Daniel CK | Karmen, Paul
MM | 1 | Purchasing - Subcontracting | BMY | Subcontracting | Purchasing - Subcontracting |  |  | Create Purchase Order | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul | ME21N | Create Purchase Order - Advanced (ME21N) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2022-12-06 | Daniel CK | Paul, Karmen, Louie
MM | 1 | Purchasing - Subcontracting | BMY | Subcontract BOM | Purchasing - Subcontracting |  |  | Create subcontract BOM | Louie | Peter, Paul | CS01 | Create subcontract BOM |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | Purchasing - Subcontracting | BMY | Subcontract BOM | Purchasing - Subcontracting |  |  | Display subcontract BOM | Louie | Peter, Paul | CS03 | Display subcontract BOM |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | Purchasing - Subcontracting | BMY | Subcontract BOM | Purchasing - Subcontracting |  |  | Change subcontract BOM | Louie | Peter, Paul | CS02 | Change subcontract BOM |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | Purchasing - Subcontracting | BMY | Production Version | Purchasing - Subcontracting |  |  | Production version for subcontract | Louie | Peter, Paul | C223 | Production version for subcontract |  | SAP_BR_PRODN_ENG_PROC |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | Purchasing - Subcontracting | BMY | Subcontracting | Purchasing - Subcontracting |  |  | Receive Goods from Subcontracting PO | Louie | Peter, Paul | MIGO | Post Goods Movement (MIGO) |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 3. Baseline Completed | 3 |  | Daniel CK | Completed |  | 2022-12-06 | Daniel CK | Paul, Karmen, Louie
MM | 1 | Consumable Purchasing | BNX | Consumable Purchasing - Non-stock Items | Consumable Purchasing |  |  | Create Purchase Order | Louie | Peter, Paul | ME21N | Create Purchase Order - Advanced | create | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-24 | Daniel CK | Karmen, Louie
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 6 | Record Inspection Results | Kim,Ian,Devanshi,Marzena, samriti,Zuber,Demetra,Chirag,praful, | Demetra |  | Record Inspection Results |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 7 | Display Quality Engineer Overview | Kim,Ian,Devanshi,Marzena, samriti,Zuber,Demetra,Chirag,praful | Demetra |  | Quality Engineer Overview |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 8 | Make Usage Decision | Kim,Ian,Devanshi,Marzena, samriti,Zuber | Demetra |  | Manage Usage Decisions |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
QM | 1 | Quality Management in Discrete Manufacturing | 1E1 | Quality Management in Discrete Manufacturing | Quality Management in Manufacturing Process |  | 9 | Display Material Stock after Quality Inspection | Kim,Ian,Devanshi,Marzena, samriti,Zuber,Demetra,Chirag,praful, Courtney, Esther, Darshand, Mike, Karen | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC |  |  |  |  | SAP-PP-TS-003-01 - Make to Stock
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 1 | Display Inspection Plan for Inspection Characteristics | Kim,Ian,Devanshi,Marzena, samriti,Zuber,Demetra,Chirag,praful | Demetra | QP03 | Display Inspection Plan (QP03) |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 2 | Display Material Stock before Goods Receipt | Kim,Ian,Devanshi,Marzena, samriti,Zuber,Demetra,Chirag,praful, Courtney, Esther, Darshand, Mike, Karen | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 3 | Display Material Stock Before Quality Inspection | Kim,Ian,Devanshi,Marzena, samriti,Zuber,Demetra,Chirag,praful, Courtney, Esther, Darshand, Mike, Karen | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 4 | Display Quality Technician Overview | Kim,Ian,Devanshi,Marzena, samriti,Zuber,Demetra,Chirag,praful | Demetra |  | Quality Technician Overview |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
FI | 1 | FI Month End | BGC | GL - Report | Reporting |  |  | General Ledger Overview | All Finance | All Finance |  | General Ledger Overview (F2445). |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
FI | 1 | Accounts Payable | J45 | AP - Daily Processing | AP - Daily Processing |  |  | Reconcile GR/IR Accounts (F3302) | Jasleen, Milan | Wendy, Jen |  | Reconcile GR/IR Accounts (F3302) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2023-01-18 | Gil | Jennifer
FI | 1 | FI Month End | J58 | GL - Daily Processing | Daily Processing |  |  | Post Recurring Journal Entry | Jasleen, Eva, Colin, Milan | Jen |  | Manage Recurring Journal Entries (F1598) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Not Started | 2022-11-25
FI | 1 | General Ledger | J58 | GL - Daily Processing | Daily Processing |  |  | Upload General Journal Entries | Jasleen, Eva, Colin, Milan | Jen |  | Upload General Journal Entries (F2548) | AccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 5 | Display Open Inspection Lots | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful, Courtney, Esther, Darshand, Mike, Karen, | Demetra |  | Manage Inspection Lots |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
MM | 1 | Purchasing - Inventory | J45 | Procurement of Direct Materials | Purchasing - Inventory |  |  | Monitor Purchase Order Items (Optional) | Louie | Peter, Paul |  | Monitor Purchase Order Items (F2358) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Purchasing - Inventory | J45 | Procurement of Direct Materials | Purchasing - Inventory |  |  | Approve Purchase Order (Optional) | Paul/Peter/Mark | Peter, Paul |  | My Inbox - All Items (F0862). |  | SAP_BR_MANAGER |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-24 | Daniel CK | Karmen, Louie
MM | 1 | Purchasing - Inventory | J45 | Procurement of Direct Materials | Purchasing - Inventory |  |  | Create Purchase Order | Karmen/ - Chris/Jackson, Louie | Peter, Paul | ME21N | Create Purchase Order - Advanced (ME21N) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 1 |  | Daniel CK | Completed |  | 2022-11-25 | Daniel CK | Karmen, Louie
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 6 | Record Inspection Results | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Chirag, Praful, | Demetra |  | Record Inspection Results |  | SAP_BR_QUALITY_TECHNICIAN |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 7 | Display Quality Engineer Overview | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra |  | Quality Engineer Overview |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 8 | Make Usage Decision | Kim, Ian, Devanshi, Marzena, Samriti, Zuber | Demetra |  | Manage Usage Decisions |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 9 | Display Material Stock after Quality Inspection | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful, Courtney, Esther, Darshand, Mike, Karen | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 10 | Print Certificate of Compliance | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 4 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 11 | Print Certificate of Manufacture | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 4 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Procurement | 1FM | Quality Management in Procurement | Quality Management in Procurement |  | 12 | Print Customer Letter | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 4 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Stock Handling | 1MR | Quality Management in Discrete Manufacturing | Quality Management in Stock Handling |  | 1 | Display Material Stock before Goods Posting | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful, Courtney, Esther, Darshand, Mike, Karen | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Stock Handling | 1MR | Quality Management in Discrete Manufacturing | Quality Management in Stock Handling |  | 2 | Post Material from Unrestricted/Blocked Stock to Quality Inspection Stock | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra | MIGO | Transfer Stock-In-Plant |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Stock Handling | 1MR | Quality Management in Discrete Manufacturing | Quality Management in Stock Handling |  | 3 | Display Material Stock Before Quality Inspection | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful, Courtney, Esther, Darshand, Mike, Karen | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Stock Handling | 1MR | Quality Management in Discrete Manufacturing | Quality Management in Stock Handling |  | 4 | Make Usage Decision | Kim, Ian, Devanshi, Marzena, Samriti, Zuber | Demetra |  | Manage Usage Decisions |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management in Stock Handling | 1MR | Quality Management in Discrete Manufacturing | Quality Management in Stock Handling |  | 5 | Display Material Stock after Quality Inspection | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful, Courtney, Esther, Darshand, Mike, Karen | Demetra | MMBE | Stock - Single Material |  | SAP_BR_WAREHOUSE_CLERK |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
FI | 1 | General Ledger | J58 | GL - Daily Processing | Daily Processing |  |  | Manage Journal Entries - templates | Jasleen, Eva, Colin, Milan | Jen |  | Manage Journal Entry Templates (F3803) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Daily Processing | Daily Processing |  |  | Post with Clearing | Jasleen, Eva, Colin, Milan | Jen |  | Post General Journal Entries (F0718 ) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Daily Processing | Daily Processing |  |  | Reverse Accrual/Deferral Journal Entry | Jasleen, Eva, Colin, Milan | Jen | F.81 | Manage Journal Entries (F0717) | RecurringAccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Daily Processing | Daily Processing |  |  | Display Document Flow | Jasleen, Eva, Colin, Milan | Wendy, Jen |  | Display Document Flow | AccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Display Changes to G/L Accounts In Chart of Accounts | Milan | Wendy, Jen | FSP4 | G/L Account Changes Chart of Accounts View |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Display Changes to G/L Accounts in Company Code | Milan | Wendy, Jen | FSS4 | G/L Account Changes Company Code View |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | G/L Account Changes Central View | Milan | Wendy, Jen | FS04 | G/L Account Changes - Central View |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Import Foreign Exchange Rates | Colin | Milan, Jen |  | Import Foreign Exchange Rates (F2092) | RecurringAccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-04 | Gil | Wendy, Jen
QM | 1 | Quality Management with Trackwise | TKW | Quality Management with Trackwise | Quality Management with Trackwise |  | 1 | Assign Material Status for Change Control | Phase 2 | Demetra | MM02 | Change Material (MM02) |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Quality Management with Trackwise | TKW | Quality Management with Trackwise | Quality Management with Trackwise |  | 2 | Make Usage Decision and review the warning message | Phase 2 | Demetra |  | Manage Usage Decisions |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 5 |  | AlexC | Not Started |  |  | AlexC
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Maintain Exchange Rates | Colin | Milan, Jen | OB08 | Maintain Exchange Rates | RecurringAccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-04 | Gil | Wendy, Jen
QM | 1 | Quality Planning | QPL | Quality Planning | Material Master |  | 1 | Extend Material Master – Quality Management view | Zuber, Ian, Demetra, Kim | Demetra | MM01 | Create Material (MM01) |  | SAP_BR_QUALITY_PLANNER |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos |  |  |  | SAP-QM-TS-001-01 - Quality Planning
QM | 1 | Quality Planning | QPL | Quality Planning | Material Master |  | 2 | Maintain Inspection Rule | Zuber, Ian, Demetra, Kim | Demetra | /SCWM/QRSETUP | Maintain Inspection Rules (/SCWM/QRSETUP) |  | SAP_BR_QUALITY_PLANNER |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos |  |  |  | SAP-QM-TS-001-01 - Quality Planning
QM | 1 | Quality Planning | QPL | Quality Planning | Inspection Planning |  | 3 | Create Master Inspection Characteristic | Zuber, Ian, Demetra, Kim | Demetra | QS21 | Create Master Inspection Characteristic (QS21) |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos |  |  |  | SAP-QM-TS-001-01 - Quality Planning
QM | 1 | Quality Planning | QPL | Quality Planning | Inspection Planning |  | 4 | Review Master Inspection Characteristics | Zuber, Ian, Demetra, Kim | Demetra |  | Display Master Inspection Characteristics |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos |  |  |  | SAP-QM-TS-001-01 - Quality Planning
QM | 1 | Quality Planning | QPL | Quality Planning | Sampling |  | 5 | Create Sampling Scheme and Sampling Plan | Zuber, Ian, Demetra, Kim | Demetra | QDP1 | Create Sampling Scheme (QDP1) |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos |  |  |  | SAP-QM-TS-001-01 - Quality Planning
QM | 1 | Quality Planning | QPL | Quality Planning | Sampling |  | 6 | Create Sampling Procedure | Zuber, Ian, Demetra, Kim | Demetra | QDV1 | Create Sampling Procedure (QDV1) |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos |  |  |  | SAP-QM-TS-001-01 - Quality Planning
QM | 1 | Quality Planning | QPL | Quality Planning | Sampling |  | 7 | Create Sample-Drawing Procedure | Zuber, Ian, Demetra, Kim | Demetra |  | Edit Sample-Drawing Procedure |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos |  |  |  | SAP-QM-TS-001-01 - Quality Planning
QM | 1 | Quality Planning | QPL | Quality Planning | Inspection Planning |  | 8 | Create Inspection Plan | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful | Demetra | QP01 | Create Inspection Plan (QP01) |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 3. Baseline Completed | 1 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos |  |  |  | SAP-QM-TS-001-01 - Quality Planning
FI | 1 | FI Month End | J58 | GL - Month end Processing | Monthly Processing |  |  | Manage Posting Periods | Milan | Wendy, Jen |  | Manage Posting Periods | RecurringAccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-04 | Gil | Wendy, Jen
QM | 1 | Quality Management in Procurement | QPL | Quality Planning | Quality Management in Procurement |  | 1 | Create Quality Info Record: Procurement | Zuber, Ian, Demetra, Kim, Neena, Anne, Roxana, Ruchita, Branka, Percival | Demetra | QI01 | Create Quality Info Record: Procurement (QI01) |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 3. Baseline Completed | 4 |  | AlexC | WIP |  |  | AlexC | Demetra Maragos
FI | 1 | FI Month End | J58 | GL - Report | Reporting |  |  | Trial Balance | All Finance | All Finance |  | Trial Balance |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
FI | 1 | FI Month End | J58 | GL - Report | Reporting |  |  | Prepare Tax Report Canada | Colin | Milan, Jen, Wendy | S_ALR_87012394 | Prepare Tax Report Canada | AccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Not Started | 2023-01-06
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Edit Company Code Assignment Profit Centers | Milan | Wendy, Jen | KE56 | Edit Company Code Assignment - Profit Centers (KE56) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Edit Master Data - Profit Centers - Collective | Milan | Wendy, Jen |  | Edit Profit Centers - Collective (KE55) | GLAccount | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Where-Used List - Profit Centers (F3751) | Milan | Wendy, Jen |  | Where-Used List - Profit Centers (F3751) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58 | GL - Master Data | Master Data |  |  | Change Log - Profit Centers (F3810) | Milan | Wendy, Jen |  | Change Log - Profit Centers (F3810) | ProfitCenter | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-18 | 2022-11-17 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | FI Month End | J58 | GL - Report | Reporting |  |  | Balance Sheet / Income Statement (F0708) | All Finance | All Finance |  | Balance Sheet / Income Statement (F0708) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-06 | 2023-01-05 | Gil | Wendy, Jen
FI | 1 | FI Month End | J58 | GL - Report | Reporting |  |  | Balance Sheet / Income Statement - Multidimensional (F3084) | All Finance | All Finance |  | Balance Sheet / Income Statement - Multidimensional (F3084) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Completed | 2023-01-23 | 2023-01-05 | Gil | Wendy, Jen
FI | 1 | General Ledger | J58 | GL - Daily Processing | Daily Processing |  |  | Display Journal Entries - in T-Account View | Jasleen, Eva, Colin, Milan | Jen |  | Display Journal Entries (F3664) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 | NEW | Gil | Completed | 2023-01-23 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Display G/L Account Line Items – Reporting View | Jasleen, Eva, Colin, Milan | Wendy, Jen |  | Display Line Items in General Ledger (F2217) | AccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Verify General Journal Entries | Jasleen, Eva, Colin, Milan | Jen |  | Verify General Journal Entries - For Requester (F2547) | LedgerGLLineItem | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58, 1GA | GL - Report | Reporting |  |  | Journal Entry Analyzer | All Finance | All Finance |  | Journal Entry Analyzer | GLAccount | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Reset Cleared Items | Jasleen, Eva, Colin, Milan | Jen | FBRA | Reset Cleared Items (F2223) | AccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Clear G/L Accounts | Jasleen, Eva, Colin, Milan | Jen |  | Clear G/L Accounts - Manual Clearing (F1579) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Not Started | 2022-11-25 | 2022-11-30 | Gil
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Display GL Account Balances | All Finance | All Finance |  | Display G/L Account Balance (F0707) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Manage Journal Entries | Milan | Wendy, Jen |  | Manage Journal Entries (F0717) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Post General Journal Entries | Jasleen, Eva, Colin, Milan | Jen |  | Post General Journal Entries (F0718 ) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Reverse General Journal Entries | Jasleen, Eva, Colin, Milan | Jen |  | Manage Journal Entries (F0717) | AccountingDocument | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-22 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | General Ledger | J58, 1GA | GL - Daily Processing | Daily Processing |  |  | Verify General Journal Entries | Jasleen, Eva, Colin, Milan | Jen |  | Verify General Journal Entries For Processor (Inbox) (F2728) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | On-Hold | 2022-11-25 | 2023-01-27 | Gil
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Display Customer Balances (F0703). | Eva | Milan, Jen, Wendy |  | Display Customer Balances (F0703). |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2023-01-25 |  | Eva, Jen
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Reset Cleared Items - FBRA (FBRA) | Eva | Milan, Jen |  | Reset Cleared Items - FBRA (FBRA) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | FI Month End | J58, 1GA | GL - Month end Processing | Monthly Processing |  |  | Carry Forward Balances | All Finance | All Finance |  | Carry Forward Balances (F1596) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 3 |  | Gil | Not Started | 2023-01-06
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Reverse Individual Documents | Eva | Milan, Jen |  | Manage Journal Entries (F0717) |  | SAP_BR_GL_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Create Outgoing Invoices (FB70) | Eva (for CPDN only) | Milan, Jen |  | Create Outgoing Invoices (FB70) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2023-01-25 |  | Eva, Jen
FI | 1 | Accounts Receivable | J59 | AR - Master Data | Master Data |  |  | Maintain Business Partner (BP) | Eva/SD/MM/MD | Milan, Jen, Wendy |  | Maintain Business Partner (BP) |  | AP_BR_BUPA_MASTER_SPECIALIST |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-08 | Gil
FI | 1 | Accounts Receivable | J59 | AR - Master Data | Master Data |  |  | Display Customer List (F2640) | Eva | Milan, Jen, Wendy |  | Display Customer List (F2640) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2023-01-25 |  | Eva, Jen
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Manage Customer Line Items (F0711) | Eva | Milan, Jen, Wendy |  | Manage Customer Line Items (F0711) |  | SAP_BR_AR_ACCOUNTANT |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-12 | Gil
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Clear Open Items | Jasleen | Milan, Jen |  | Clear Outgoing Payments (F1367) | Supplier | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2023-01-24 | 2023-01-23 | Gil | Jen
FI | 1 | Accounts Payable | J60 | AP - Master Data | AP - Master Data |  |  | Display Changes to Suppliers S_ALR_87012089 | Jasleen, MD | Milan, Jen, Wendy | S_ALR_87012089 | Display Changes to Suppliers S_ALR_87012089 |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Manage Payment Blocks | Jasleen | Milan, Jen |  | Manage Payment Blocks (F0593) | Supplier | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2023-01-24 | 2023-01-23 | Gil | Jen
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Post Down Payment | Jasleen | Milan, Jen |  | Post Outgoing Payments (F1612) | Supplier | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2023-01-24 | 2023-01-23 | Gil | Jen
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Post Outgoing payment | Jasleen | Milan, Jen |  | Post Outgoing Payments (F1612) | Supplier | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Create Single Payment | Jasleen | Milan, Jen |  | Create Single Payment (F0743) | Supplier | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Release Payment Proposal | Milan, Wendy | Scott, Jen |  | Manage Automatic Payments (F0770) |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Revise Payment Proposal | Jasleen | Milan, Jen |  | Revise Payment Proposals - Automatic Payment (F0771) |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Manage Checkbooks | Jasleen | Milan, Jen |  | Manage Outgoing Checks (F1578) |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Master Data | AP - Master Data |  |  | Complete Supplier master data | Jasleen | Milan, Jen, Wendy | BP | Maintain Business Partner |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-23 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Outgoing Payment | AP Payments |  |  | Schedule Payment Proposal | Jasleen | Milan, Jen |  | Manage Automatic Payments - Scheduling (F0770) | AutomaticPayment | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | import supplier invoices | Jasleen | Milan, Jen |  | Import Supplier Invoices (F3041) |  | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-23 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Create Supplier Invoice without PO/GR relation | Jasleen | Milan, Jen |  | Create incoming invoices (FB60). |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Cancelled | 2022-12-02 | 2022-11-23 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 / BNX | AP - Daily Processing | AP - Daily Processing |  |  | Create Supplier Invoice with PO/GR relation | Jasleen | Milan, Jen |  | Create Supplier Invoice (F0859) | SupplierPaymentAnalysisKPI | SAP_BR_AP_MANAGER |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-23 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 / BNX | AP - Daily Processing | AP - Daily Processing |  |  | Create Supplier Invoice with PO/GR relation (with Invoice Reduction) | Jasleen | Milan, Jen |  | Manage Supplier Invoice (F0859) |  | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2023-01-18 | Gil | Jennifer
FI | 1 | Accounts Payable | J60 / BNX | AP - Daily Processing | AP - Daily Processing |  |  | Create Supplier Invoice - Advanced (MIRO) | Jasleen | Milan, Jen | MIRO | Create Supplier Invoice - Advanced (MIRO) | SupplierInvoice | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Cancelled | 2022-12-02 | 2022-11-23 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Bank Accounting & Cash Operations | J77 | AP - Outgoing Payment | Payments |  |  | Maintain Payment Approver | Wendy | Scott |  | Maintain Payment Approver - For Multiple Bank Accounts |  | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Bank Accounting & Cash Operations | J78 | AP - Outgoing Payment | Payments |  |  | Approve Bank Payments | Milan | Wendy, Jen |  | Approve Bank Payments |  | SAP_BR_CASH_SPECIALIST |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Bank Accounting & Cash Operations | J78 | AP - Outgoing Payment | Payments |  |  | Monitor Payments | Jasleen | Milan, Jen, Wendy |  | Monitor Payments - Item (F0711) | PaymentItem | SAP_BR_AP_ACCOUNTANT |  |  |  | 3. Baseline Completed | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Manage Bank Statement Reprocessing Rules | Eva, Colin | Milan, Jen, Wendy |  | Manage Bank Statement Reprocessing Rules (F3555) |  | SAP_BR_CASH_SPECIALIST |  |  |  | 5. On Hold by NTT | 4 | NEW | Gil | On-Hold
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | ZFI_UPLOAD_PYMT | Eva | Milan, Jen | ZFI_UPLOAD_PYMT | ZFI_UPLOAD_PYMT |  | custom trasaction need to create role |  |  |  | 3. Baseline Completed | 4 | NEW | Gil | Completed | 2022-12-09 | 2023-01-25 | Gil | Eva, Jen
FI | 1 | Accounts Payable | J45 | AP - Daily Processing | AP - Daily Processing |  |  | Clear GR/IR Clearing Account | Jasleen, Milan | Wendy, Jen | MR11 | Clear GR/IR Clearing Account (MR11) |  | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  |  |  | 7. QA Approved | 1 |  | Gil | Not Started | 2022-12-02 | 2023-01-18 | Gil | Gil
FI | 1 | Accounts Payable | J45 | AP - Daily Processing | AP - Daily Processing |  |  | Reconcile GR/IR Accounts (F3302) | Jasleen, Milan | Wendy, Jen |  | Reconcile GR/IR Accounts (F3302) |  | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2023-01-18 | Gil | Jennifer
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Overdue Receivables - Today (F1747) | Eva | Milan, Jen, Wendy |  | Overdue Receivables - Today (F1747) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Overdue Receivables - by Risk Class (F2539) | Eva | Milan, Jen, Wendy |  | Overdue Receivables - by Risk Class (F2539) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Future Receivables - Today (F1744) | Eva | Milan, Jen, Wendy |  | Future Receivables - Today (F1744) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Cash Collection Tracker - Accounts Receivable (F2925) | Eva | Milan, Jen, Wendy |  | Cash Collection Tracker - Accounts Receivable (F2925) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Accounts Receivable Overview (F3242) | Eva | Milan, Jen, Wendy |  | Accounts Receivable Overview (F3242) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Reprocessing Rate - of Incoming Payments (F1619) | Eva | Milan, Jen |  | Reprocessing Rate of Incoming Payments (F1619) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Total Receivables - Today (F1748) | Eva | Milan, Jen, Wendy |  | Total Receivables - Today (F1748) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Days Sales Outstanding - Last 12 Months (F1741) | Eva | Milan, Wendy, Jen, Scott |  | Days Sales Outstanding - Last 12 Months (F1741) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Days Beyond Terms - Last 12 Months (F1739) | Eva | Milan, Jen, Wendy |  | Days Beyond Terms - Last 12 Months (F1739) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Receivable | J59 | AR - Reporting | Reporting |  |  | Display Item Change Log - Customer (F2681) | Eva | Milan, Jen, Wendy |  | Display Item Change Log - Customer (F2681) |  | SAP_BR_AR_MANAGER |  |  |  | 7. QA Approved | 2 |  | Gil | Completed | 2022-12-09 | 2022-12-15 | Gil | Jennifer, Eva
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Aging Analysis | Jasleen | Milan, Jen, Wendy |  | Aging Analysis - Payable Amount | AutomaticPayment | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Automatic and Manual Payments Analysis | Jasleen | Milan, Jen, Wendy |  | Automatic and Manual Payments - Payments for Last Year (F1749) | AutomaticPayment | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Cash Discount Forecast | Jasleen | Milan, Jen, Wendy |  | Cash Discount Forecast - Available Amount | AgingAnalysisKPI | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Cash Discount Utilization | Jasleen | Milan, Jen, Wendy |  | Cash Discount Utilization - Today | AutomaticAndManualPaymentsKPI | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Display Supplier List | Jasleen | Milan, Jen, Wendy |  | Display Supplier List (F1861) |  | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Future Payables | Jasleen | Milan, Jen, Wendy |  | Future Payables - Today | DaysPayablesOutstandingKPI | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Invoice Processing Analysis | Jasleen | Milan, Jen, Wendy |  | Invoice Processing Analysis - Today | Supplier | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Overdue Payables | Jasleen | Milan, Jen, Wendy |  | Overdue Payables - Today | FuturePayablesKPI | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Supplier Payment Analysis | Jasleen | Milan, Jen, Wendy |  | Supplier Payment Analysis - Open Payments | InvoiceProcessingTimeKPI | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Reporting | Reporting |  |  | Accounts Payable Overview (F2917) | Jasleen | Milan, Wendy, Jen, Scott |  | Accounts Payable Overview (F2917) | OverduePayablesKPI | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Create Down Payment Request | Jasleen | Milan, Jen |  | Manage Supplier Down Payment Request (F1688) | Supplier | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2023-01-24 | 2023-01-23 | Gil | Jen
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Reset Cleared Items | Jasleen | Milan, Jen |  | Reset Cleared Items (F2223) | ClearingAccountingDocument | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Reset and Reverse Cleared Items | Jasleen | Milan, Jen |  | Reset Cleared Items (F2223) | ClearingAccountingDocument | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-30 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | View Supplier Balance | Jasleen | Milan, Jen, Wendy |  | Display Suppier Balances (F0701) | Vendor | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-23 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | View Supplier Line Items | Jasleen | Milan, Jen, Wendy |  | Manage Supplier Line Items (F0712) | Supplier | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-23 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Manage Checkbooks | Jasleen | Milan, Jen, Wendy |  | Manage Checkbooks (F1577) |  | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Approve Bank Payments (F0673A) | Milan, Wendy | Scott, Jen |  | Approve Bank Payments (F0673A) |  | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-12-02 | 2022-11-29 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
FI | 1 | Accounts Payable | J60 | AP - Daily Processing | AP - Daily Processing |  |  | Display Item Change Log | Jasleen | Milan, Jen, Wendy |  | Display Item Change Log - Customer (F2681) |  | SAP_BR_AP_MANAGER |  |  |  | 7. QA Approved | 1 |  | Gil | Not Started | 2022-12-02 | 2022-12-02 | Gil | Jen, Wendy
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Reprocess Lockbox Items | Eva | Milan, Jen |  | Reprocess Lockbox Items (F3398) |  | SAP_BR_CASH_SPECIALIST_US |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2023-01-25 |  | Eva, Jen
FI | 1 | Accounts Payable | J60 / BNX | AP - Master Data | AP - Master Data |  |  | Supplier Invoices List | Jasleen | Milan, Jen, Wendy |  | Supplier Invoices List (F1060A) | SupplierInvoice | SAP_BR_AP_ACCOUNTANT |  |  |  | 7. QA Approved | 1 |  | Gil | Completed | 2022-11-25 | 2022-11-23 | Gil | Wendy Kwan, Jennifer Leung, Azam Hussain
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 1 | List Incomplete Sales Documents | Bana | Shannon |  | List Incomplete Sales Documents (F2430) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 2 | Track Sales Orders | Bana, Cyrus, Gladys, Scott | Bana,Scott,Shannon |  | Track Sales Orders (F2577) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 3 | Review Sales Order Fulfillment Issues | Bana, Cyrus, Gladys, Scott | Bana,Scott,Shannon |  | Sales Order Fulfillment - Analye Issues (F0029A) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 5 | Review Sales Documents Blocked for Delivery | Bana, Cyrus, Gladys, Scott | Bana,Scott,Shannon |  | Sales Order Fulfillment - Resolve Delivery Block (F0029A) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, | Va14L | Bana
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 6 | Review Sales Documents Blocked for Billing | Bana, Cyrus, Gladys, Scott | Bana,Scott,Shannon |  | Sales Order Fulfillment - Resolve Billing Block F0029A) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, | V23 | Bana
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 7 | Review Sales Orders Due for Delivery | Bana, Cyrus, Gladys, Scott | Bana,Scott,Shannon |  | My Sales Order Items Due for Delivery |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Not Started | 2023-01-23 |  | Ahmad |  |  | Bana
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 8 | Review Log of Delivery Creation | Bana, Cyrus, Gladys, Scott, Louie | Bana,Scott,Shannon |  | Analyze Delivery Logs (F0870A) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 9 | Review Outbound Deliveries for Goods Issue | Louie | Paul |  | My Outbound Delivery Monitor (VL06O) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Not Started | 2023-01-23 |  | Ahmad
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 10 | Review Billing Due List | Eva | Milan |  | Create Billing Documents (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 11 | Review Log of Collective Invoice Creation | Eva and SD for support - | Shannon, Milan |  | Schedule Billing Creation (F1519) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Not Started | 2023-02-08 |  | Ahmad
SD | 1 | Sales Order Reporting | BKK | Sales Order Fulfillment Monitoring | Reporting |  | 12 | Review List of Blocked Billing Documents (for Accounting) | Bana, Cyrus, Gladys,Eva | Shannon, Milan, Jen |  | Manage Billing Documents (F0797) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly,
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 1 | Create Sales Order | Bana, Cyrus, Gladys | Shannon |  | Manage Sales Orders Without Charge (F2305) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Not Started | 2023-02-20 | 2023-02-13 | Ahmad | Bana
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 2 | Create Attachment for Sales Order (Optional) | Bana, Cyrus, Gladys | Shannon |  | Manage Sales Orders Without Charge (F2305) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Not Started | 2023-02-20 | 2023-02-13 | Ahmad
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 3 | Create Delivery | Louie, Bana, Cyrus, Gladys | Shannon |  | Create Outbound Deliveries - From Sales Orders (F0869A) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Not Started | 2023-02-20 | 2023-02-13 | Ahmad
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 4 | Create Attachment for Delivery (Optional) | Louie & Bana, Cyrus, Gladys | Shannon |  | Display Outbound Delivery (VL03N) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Not Started | 2023-02-20 | 2023-02-13 | Ahmad
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 5 | Execute Picking | Louie | Paul |  | My Outbound Delivery Monitor (VL06O) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Not Started | 2023-02-20 | 2023-02-13 | Ahmad
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 6 | Check Batches (Optional) | Bana, Louie | Cyrus, Gladys |  | Change Outbound Delivery (VL02N) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Not Started | 2023-02-20 | 2023-02-13 | Ahmad
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 7 | Post Goods Issue | Louie | Paul |  | My Outbound Delivery Monitor (VL06O) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Not Started | 2023-02-20 | 2023-02-13 | Ahmad
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 8 | Create Pro Forma Invoice | Bana, Cyrus, Gladys | Shannon |  | Create Billing Documents (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 9 | Create Customer Invoice | Bana, Cyrus, Gladys, Eva (CPDN only) | Shannon, Milan, Jen |  | Create Billing Documents (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Sales Order Processing | BDA | Free of Charge Delivery | Delivery Processing |  | 10 | Create Attachment for Billing (Optional) | Louie | Bana |  | Manage Billing Documents (F0797) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 2 |  | Ahmad | Not Started | 2023-02-20 | 2023-01-23 | Ahmad
SD | 1 | Credits and Debits | 1EZ | Credit Memo Processing | Credit Memo Processing |  | 1 | Create Credit Memo Requests | Bana, Cyrus, Gladys | Shannon |  | Manage Credit Memo Requests (F1989) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-02-13 |  | Ahmad
SD | 1 | Credits and Debits | 1EZ | Credit Memo Processing | Credit Memo Processing |  | 2 | Create Attachment for Sales Order (Optional) | Bana, Cyrus, Gladys | Shannon |  | Manage Credit Memo Requests (F1989) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-02-13 |  | Ahmad
SD | 1 | Credits and Debits | 1EZ | Credit Memo Processing | Credit Memo Processing |  | 6 | Change Credit Memo Request | Bana, Cyrus, Gladys | Shannon |  | Manage Credit Memo Requests (F1989) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-02-13 |  | Ahmad
SD | 1 | Credits and Debits | 1EZ | Credit Memo Processing | Credit Memo Processing |  | 7 | Create Credit Memo | Eva | Milan, Jen |  | Create Billing Documents (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Credits and Debits | 1EZ | Credit Memo Processing | Credit Memo Processing |  | 8 | Create Attachment for Sales Order (Optional) | Eva | Milan, Jen |  | Manage Sales Orders (F1873) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-02-13 |  | Ahmad
SD | 1 | Credits and Debits | 1F1 | Debit Memo Processing | Debit Memo Processing |  | 1 | Create Debit Memo Request | Eva, Bana | Shannon, Milan, Jen |  | Manage Debit Memo Requests (F1988) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-02-13 |  | Ahmad
SD | 1 | Credits and Debits | 1F1 | Debit Memo Processing | Debit Memo Processing |  | 2 | Create Attachment for Debit Memo Request (Optional) | Eva, Bana | Shannon, Milan, Jen |  | Manage Debit Memo Requests (F1988) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-02-13 |  | Ahmad
SD | 1 | Credits and Debits | 1F1 | Debit Memo Processing | Debit Memo Processing |  | 3 | Remove Billing Block | Eva | Milan, Jen | VA03 | Display Sales Orders (VA03) Sales Order Fulfillment - Resolve Billing Block (F0029) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-02-13 |  | Ahmad
SD | 1 | Credits and Debits | 1F1 | Debit Memo Processing | Debit Memo Processing |  | 4 | Create Debit Memo | Eva | Milan, Jen |  | Create Billing Documents (F0798)- Billing Due List Items |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Credits and Debits | 1F1 | Debit Memo Processing | Debit Memo Processing |  | 5 | Create Attachment for Billing (Optional) | Eva | Milan, Jen | VF03 | Display Billing Documents (VF03) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-02-13 |  | Ahmad
SD | 1 | Credits and Debits | BDQ | Invoice Correction Process with Debit Memo | Invoice Correction Process with Debit Memo |  | 1 | Create Debit Memo Request | Eva | Milan, Jen |  | Manage Debit Memo Requests (F1988) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Completed | 2022-12-22 | 2022-12-14 | Ahmad | Eva, Jenn, Remo, Bana, Shannon
SD | 1 | Credits and Debits | BDQ | Invoice Correction Process with Debit Memo | Invoice Correction Process with Debit Memo |  | 2 | Create Attachment for Sales Order (Optional) | Eva | Milan, Jen |  | Manage Debit Memo Requests (F1988) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2022-12-22 |  | Ahmad
SD | 1 | Credits and Debits | BDQ | Invoice Correction Process with Debit Memo | Invoice Correction Process with Debit Memo |  | 3 | Remove Billing Block | Eva | Milan, Jen |  | Release Sales Orders (F0029A) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Completed | 2022-12-22 | 2022-12-14 | Ahmad | Eva, Jenn, Remo, Bana, Shannon
SD | 1 | Credits and Debits | BDQ | Invoice Correction Process with Debit Memo | Invoice Correction Process with Debit Memo |  | 4 | Create Debit Memo | Eva | Milan, Jen |  | Create Billing Documents (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Completed | 2022-12-22 | 2022-12-14 | Ahmad | Eva, Jenn, Remo, Bana, Shannon
SD | 1 | Credits and Debits | BDQ | Invoice Correction Process with Debit Memo | Invoice Correction Process with Debit Memo |  | 5 | Create Attachment for Billing (Optional) | Eva | Milan, Jen |  | Display Billing Documents (VF03) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2022-12-22 |  | Ahmad
SD | 1 | Credits and Debits | BKL | Invoice Correction Process with Credit Memo | Credit Memo |  | 1 | Create Credit Memo Request | Eva | Milan, Jen |  | Manage Credit Memo Requests (F1989) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2022-12-22 | 2022-12-14 | Ahmad | Eva, Jenn, Remo, Bana, Shannon |  | Eva | BPP-SD- Create RK Credit Memo Request.docx
SD | 1 | Credits and Debits | BKL | Invoice Correction Process with Credit Memo | Credit Memo |  | 2 | Create Attachment for Sales Orders (Optional) | Eva | Milan, Jen |  | Manage Credit Memo Requests (F1989) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Not Started | 2022-12-22 |  | Ahmad |  |  | Eva | BPP-SD- Create RK Credit Memo Request.docx
SD | 1 | Credits and Debits | BKL | Invoice Correction Process with Credit Memo | Credit Memo |  | 4 | Create Credit Memo | Eva | Milan, Jen |  | Create Billing Documents (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2022-12-22 | 2022-12-14 | Ahmad | Eva, Jenn, Remo, Bana, Shannon |  | ? | BPP-SD- Create Billing Documents.docx
SD | 1 | Credits and Debits | BKL | Invoice Correction Process with Credit Memo | Credit Memo |  | 5 | Create Attachment for Billing (Optional) | Eva | Milan, Jen |  | Manage Billing Documents (F0797) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2022-12-22 | 2022-12-14 | Ahmad | Eva, Jenn, Remo, Bana, Shannon |  | ? | yes
SD | 1 | Customer Returns | BDD | Customer Returns | Customer Returns |  | 1 | Create Return Order | Bana, Cyrus, Gladys | Shannon | VA01 | Create Sales Orders - VA01 (VA01) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-01-30 |  | Ahmad
SD | 1 | Customer Returns | BDD | Customer Returns | Customer Returns |  | 2 | Create Attachment for Sales Order (Optional) | Bana, Cyrus, Gladys | Shannon |  | Manage Customer Returns (F1708) |  | SAP_BR_RETURNS_REFUND_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-01-30 |  | Ahmad
SD | 1 | Customer Returns | BDD | Customer Returns | Customer Returns |  | 3 | Create Return Delivery | Louie | Paul | VL01n | Create Outbound Delivery - With Order Reference (VL01N) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 2. WIP | 4 |  | Ahmad | Not Started | 2023-01-30 |  | Ahmad
SD | 1 | Customer Returns | BDD | Customer Returns | Customer Returns |  | 4 | Create Attachment for Delivery (Optional) | Louie | Paul | VL03n | Display Outbound Delivery (VL03N) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-01-30 |  | Ahmad
SD | 1 | Customer Returns | BDD | Customer Returns | Customer Returns |  | 5 | Post Goods Receipt | Louie | Paul |  | My Outbound Delivery Monitor (VL06O) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 2. WIP | 4 |  | Ahmad | Not Started | 2023-01-30 |  | Ahmad
SD | 1 | Customer Returns | BDD | Customer Returns | Customer Returns |  | 6 | Remove Billing Block | Eva | Milan, Jen |  | Manage Customer Returns (F1708) |  | SAP_BR_RETURNS_REFUND_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Not Started | 2023-01-30 |  | Ahmad
SD | 1 | Customer Returns | BDD | Customer Returns | Customer Returns |  | 7 | Create Billing Document | Eva | Milan, Jen |  | Create Billing Documents - Billing Due List Items (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 4 |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Customer Returns | BDD | Customer Returns | Customer Returns |  | 8 | Create Attachment for Billing (Optional) | Eva | Milan, Jen |  | Manage Billing Documents (F0797) |  | SAP_BR_BILLING_CLERK |  |  |  | 2. WIP | 4 |  | Ahmad | Not Started | 2023-01-30 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | My Sales Overview | Bana, Cyrus, Gladys, Scott,Kelly, Shannon | Shannon, Eva, Milan, Jen, Wendy |  | My Sales Overview (F2200) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Sales Volume - Profit Margin | Kelly, FPA | Shannon, Milan, Jen, Wendy, Scott N |  | Sales Volume - Profit Margin |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Sales Volume - Credit Memos | Kelly, Eva | Shannon, Milan |  | Sales Volume - Credit Memo |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Sales Volume - Check Open Sales | Kelly | Shannon |  | Sales Volume - Check Open Sales (F2270) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Analyze Confirmations of Sales Orders ( 3 tile) | Bana, Cyrus, Gladys, Scott | Shannon |  | Sales Order Items – Confirmed, Sales Order Items – Backorders, Sales Orders - Demand Fulfillment (F2458) |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Sales Management Overview | Bana, Cyrus, Gladys, Scott | Shannon |  | Sales Management Overview (F2601) |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Delivery Performance | Louie, Bana | Shannon |  | Delivery Performance (F2878) |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Incoming Sales Orders | Louie, Scott, Bana, Arthur | Shannon |  | Incoming Sales Orders - Flexible Analysis (F1249) |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Sales Volume - Flexible Analysis | Louie, Kelly, Scott | Shannon |  | Sales Volume - Flexible Analysis (F1250) |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Customer Returns - Flexible Analysis | Louie, Bana | Shannon |  | Customer Returns (F3889, Customer Returns (W0139) |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Customer Return Rate | Kelly, FPA, Milan | Shannon |  | Customer Return Rate (F4092) |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Order Reporting | 1BS | SAP Fiori Analytical Apps for Sales | Reporting |  |  | Sales Volume - Detailed Analysis | Bana, Cyrus, Gladys, Scott, Kelly, Shannon,Jackson | Shannon, Colin, Wendy, Milan, Jen, Scott N, FPA |  | Sales Volume - Detailed Analysis (F2235) |  | SAP_BR_SALES_MANAGER |  |  |  | 3. Baseline Completed | 5 |  | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | Sales Rebates | 999 | Create Debit memo for indirect sales | Sales Rebates |  |  | create debit memo request (load from file) RICEF | Eva | Colin, Milan, Jen | Z tcode | Create Debit Memo Request |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed |  |  | Ahmad | Not Started |  |  | Ahmad
SD | 1 | Sales Rebates | 999 | Bill indirect debit memo | Sales Rebates |  |  | bill debit memo request | Colin | Milan, Jen |  | Create Billing Document |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed |  |  | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | BP maintenance |  | BP maintenance | Master Data |  |  | Create Customer sold-to | Eva, MD | Enrique | BP | create sold to |  | SAP_BR_BUPA_MASTER_SPECIALIST |  |  |  | 3. Baseline Completed | 1 | Create Sold-To | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | BP maintenance |  | BP maintenance | Master Data |  |  | Create Contact Person | Bana, Cyrus, Gladys, Eva | Shannon | BP | create contact person |  | SAP_BR_BUPA_MASTER_SPECIALIST |  |  |  | 3. Baseline Completed | 1 | Create Contact Person | Ahmad | Not Started | 2023-01-25 |  | Ahmad
SD | 1 | none | 999 | none | Master Data |  |  | Manage Customer Material Records | Bana |  |  | Manage Customer Materials |  | SAP_SD_SP_INTERNAL_SALES |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Completed | 2023-01-26 | 2023-01-26 | Ahmad | Bana |  | Bana
SD | 1 | none | 999 | none | Master Data |  |  | EDI Price List/contract xref |  |  | ZSD_EDI_PRICE | will have a tile |  | tbd |  |  |  | 4. Delta Completed/Unit Testing |  |  | Ahmad | Not Started
SD | 1 | BP maintenance |  | RICEF | Shipping |  |  | Export Ship-to to file for ATS | Louie | Paul |  | Export of Customer Records (shipto) |  | add to master data role ? |  |  |  | 3. Baseline Completed | 3 |  | Ahmad | Not Started
SD | 1 | Sales Order Processing | 2LN | Basic Available-to-Promise Processing | ATP Processing |  | 1 | Monitor Availability (co09) | Scott, Bana,Arthur,Cyrus,Gladys | Shannon | CO09 | Monitor Product Availability (CO09) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 2. WIP | 1 | View Inventory & Batch SLOCs | Ahmad | Not Started |  |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 2 | Create Sales Order | Bana, Cyrus, Gladys | Shannon |  | Manage Sales Orders (F1873) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 1 | Create Sales Order for Direct Sale Create Sales Order for Distributor Sales | Ahmad | Not Started | 2023-02-06 |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 3 | Create Attachment for Sales Order (Optional) | Bana, Cyrus, Gladys | Shannon |  | Manage Sales Orders (F1873) |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 2. WIP | 1 | Attach document to SAP doc flow | Ahmad | Not Started | 2023-02-06 |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Delivery Processing |  | 8 | Create Delivery | Louie, Bana, Cyrus, Gladys | Shannon |  | Create Outbound Deliveries - From Sales Orders (F0869A) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 | Create Delivery for Oakville Outbound Shipment | Ahmad | Not Started | wm |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 9 | Create Attachment for Delivery (Optional) | Louie, Bana, Cyrus, Gladys | Shannon |  | Display Outbound Delivery (VL03N) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 | Attach document to SAP doc flow | Ahmad | Not Started | wm |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 10 | Execute Picking | Louie | Paul |  | Manage Outbound Deliveries - VL06O (VL06O_CLOUD) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 | Pick Items for Delivery with RF | Ahmad | Not Started | wm |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 11 | Check Batches (Optional) | Bana, Louie | Cyrus, Gladys |  | Change Outbound Delivery (VL02N) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 | Select Batches Picked with RF | Ahmad | Not Started | wm |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 14 | Add Freight Costs (Optional) | Bana, Cyrus, Gladys | Shannon |  | Change Outbound Delivery (VL02N) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 2. WIP | 2 |  | Ahmad | Not Started | wm |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 15 | Post Goods Issue | Louie | Paul |  | Manage Outbound Deliveries - VL06O (VL06O_CLOUD) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 | Post Goods Issue of picked Batches | Ahmad | Not Started | wm |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 16 | Proof of Delivery (Optional) | Louie | Paul |  | POD - Change Outbound Delivery |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 2. WIP | 2 |  | Ahmad | Not Started | wm |  | Ahmad
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 18 | Create Billing Document | Bana | Shannon |  | Create Billing Documents (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 2 | Create Invoice Document | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
SD | 1 | Sales Order Processing | BD9-1 | Sell from Stock - standard order (and EDI) | Standard Order and EDI |  | 19 | Create Attachment for Billing (Optional) | Bana | Shannon |  | Display Billing Documents (VF03) |  | SAP_BR_BILLING_CLERK |  |  |  | 2. WIP | 2 |  | Ahmad | Not Started | 2023-02-08 |  | Ahmad
SD | 1 | Sales Order Processing | BD9-2 | Sell from Stock - CPDN order | CPDN Order |  | 1 | Create Sales Order | Bana, Cyrus, Gladys | Shannon | Z tcode Zi010 | Z tile |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 3. Baseline Completed | 1 |  | Ahmad | Not Started | 2023-02-06 |  | Ahmad
SD | 1 | Sales Order Processing | BD9-2 | Sell from Stock - CPDN order | CPDN Order |  | 2 | Create Delivery | Louie, Bana | Shannon |  | Create Outbound Deliveries - From Sales Orders (F0869A) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 | Create Delivery for Oakville Outbound Shipment | Ahmad | Not Started | 2023-02-06 |  | Ahmad
SD | 1 | Sales Order Processing | BD9-2 | Sell from Stock - CPDN order | CPDN Order |  | 3 | Execute Picking | Louie | Paul |  | Manage Outbound Deliveries - VL06O (VL06O_CLOUD) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 | Pick Items for Delivery with RF | Ahmad | Not Started | 2023-02-06 |  | Ahmad
SD | 1 | Sales Order Processing | BD9-2 | Sell from Stock - CPDN order | CPDN Order |  | 4 | Post Goods Issue | Louie | Paul |  | Manage Outbound Deliveries - VL06O (VL06O_CLOUD) |  | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 2 | Post Goods Issue of picked Batches | Ahmad | Not Started | 2023-02-06 |  | Ahmad
SD | 1 | Sales Order Processing | BD9-2 | Sell from Stock - CPDN order | CPDN Order |  | 5 | Create Billing Document | Bana | Shannon |  | Create Billing Documents (F0798) |  | SAP_BR_BILLING_CLERK |  |  |  | 3. Baseline Completed | 2 | Create Invoice Document | Ahmad | Completed | 2023-01-23 | 2023-01-23 | Ahmad | Bana, Remo, Scott, Kelly, |  | Bana
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Maintenance |  |  | Create Condition Contract | Jackie |  | WCOCO | Maintain Customer Condition Contracts |  | SAP_BR_INTERNAL_SALES_REP |  |  |  | 2. WIP | 1 |  | Jessica | Complete |  | 11/28, 12/1 | Jessica | Jackie, Wendy, Johnny
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Maintenance |  |  | Manage condition contracts | Jackie |  | /i4e01/si_sr | it.Smart Sales Strategic Report |  | /I4G01/SMARTBASEROLE /I4G01/SMARTREBATEROLE |  |  |  | 2. WIP | 1 |  | Jessica | Complete |  | 2022-12-06 | Jessica | Jackie, Wendy, Johnny
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Monitoring |  |  | Review business volume | Jackie |  | WB2R_BUSVOL | Display Business Volume for Condition Contracts |  | SAP_BR_BILLING_CLERK |  |  |  | 2. WIP | 1 |  | Jessica | Complete |  | 2022-12-06 | Jessica | Jackie, Wendy, Johnny
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Settlement |  |  | Create Accruals | Jackie |  | WB2R_SC | Settle Customer Condition Contracts |  | SAP_BR_BILLING_CLERK |  |  |  | 2. WIP | 1 |  | Jessica | Complete |  | 2022-12-06 | Jessica | Jackie, Wendy, Johnny
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Monitoring |  |  | Display accruals | Jackie |  | /i4e01/si_sr | it.Smart Sales Strategic Report |  | /I4G01/SMARTBASEROLE /I4G01/SMARTREBATEROLE |  |  |  | 2. WIP | 1 |  | Jessica | Complete |  | 2022-12-06 | Jessica | Jackie, Wendy, Johnny
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Settlement |  |  | Create Settlement | Jackie |  | WB2R_SC | Settle Customer Condition Contracts |  | SAP_BR_BILLING_CLERK |  |  |  | 2. WIP | 1 |  | Jessica | Complete |  | 2022-12-06 | Jessica | Jackie, Wendy, Johnny
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Monitoring |  |  | Export settlement detail (optional) | Jackie |  | /i4e01/si_sr | it.Smart Sales Strategic Report |  | /I4G01/SMARTBASEROLE /I4G01/SMARTREBATEROLE |  |  |  | 2. WIP | 1 |  | Jessica | Complete |  | 2022-12-06 | Jessica | Jackie, Wendy, Johnny
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Settlement |  |  | Print or Email settlement output | Jackie |  | WZR2 | Display Customer Settlement Document |  | SAP_BR_BILLING_CLERK |  |  |  | 2. WIP | 3 |  | Jessica | Complete |  | 2022-12-06 | Jessica | Jackie, Wendy, Johnny
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Condition Contract Maintenance |  |  | Condition Contract Mass Upload | Jackie |  |  | it.Smart Condition Contract Mass Upload |  | /I4G01/SMARTBASEROLE /I4G01/SMARTREBATEROLE |  |  |  | 3. Complete | 3 |  | Jessica | Complete |  | 2022-12-13 | Jessica | Jackie, Wendy
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Deductions & Claims Settlement |  |  | D&C Workbench Settle Deduction or Claim | Jackie |  |  | it.Smart Deductions & Claims Workbench |  | /I4G01/SMARTBASEROLE /I4G01/SMARTBILLBACKSROLE |  |  | Jessica |  |  |  | Jessica |  |  |  |  | Jackie, Wendy
Rebates | 1 | Sales Rebates | 1B6 | Sales Rebates | Accruals Adjustment |  |  | Adjust Accruals in Differential Accruals Report | Colin | Milan, Jen |  | it.Smart Differential Report |  | /I4G01/SMARTBASEROLE /I4G01/SMARTREBATEROLE |  |  | Jessica |  |  |  | Jessica |  |  |  |  | Jackie, Remo
MM | 1 | MM Master Data | MM DATA | MM DATA | Supplier Business Partner |  |  | Creating Supplier Master Data- General Data | Karmen/ - Chris/Jackson, Louie | Peter, Paul | BP | BusinessPartner | edit | SAP_BR_BUPA_MASTER_SPECIALIST |  |  | ACTIVE | 3. Baseline Completed | 5 |  | Daniel CK | Completed |  | 2023-01-04 | Daniel CK | Jennifer, Karmen
MM | 1 | MM Master Data | MM DATA | MM DATA | Supplier Business Partner |  |  | Creating Supplier Master Data- Purchasing Data (Purchasing Organization) | Karmen/ - Chris/Jackson | Peter, Paul | BP | BusinessPartner | edit | SAP_BR_BUPA_MASTER_SPECIALIST |  |  | ACTIVE | 3. Baseline Completed | 5 |  | Daniel CK | Completed |  | 2023-01-04 | Daniel CK | Jennifer, Karmen
MM | 1 | MM Master Data | MM DATA | MM DATA | Material Master Data |  |  | Material Master mass maintenance | Karmen/ - Chris/Jackson | Peter, Paul | MM17 | Material | maintainMass | SAP_BR_PRODMASTER_SPECIALIST |  |  | ACTIVE | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | MM Master Data | MM DATA | MM DATA | Material Master Data |  |  | Display Material | Karmen/ - Chris/Jackson | Peter, Paul | MM03 | Material | display | SAP_BR_PRODMASTER_SPECIALIST |  |  | ACTIVE | 3. Baseline Completed | 5 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | MM Master Data | MM DATA | MM DATA | Material Master Data |  |  | Change Material | Karmen/ - Chris/Jackson | Peter, Paul | MM02 | Material | change | SAP_BR_PRODMASTER_SPECIALIST |  |  | ACTIVE | 3. Baseline Completed | 5 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | MM Master Data | MM DATA | MM DATA | Material Master Data |  |  | Create Material | Karmen/ - Chris/Jackson | Peter, Paul | MM01 | Material | create | SAP_BR_PRODMASTER_SPECIALIST |  |  | ACTIVE | 3. Baseline Completed | 5 |  | Daniel CK | Completed |  | 2022-12-05 | Daniel CK | Paul, Karmen, Louie
MM | 1 | Supplier Evaluation | SL4 | Supplier Evaluation and Performance Monitoring | Supplier Evaluation |  |  | Display Supplier Evaluation by Price | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul |  | Supplier Evaluation by Price (F1663) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Supplier Evaluation | SL4 | Supplier Evaluation and Performance Monitoring | Supplier Evaluation |  |  | Display Supplier Evaluation by Quantity | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul |  | Supplier Evaluation by Quantity (F1661) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
MM | 1 | Supplier Evaluation | SL4 | Supplier Evaluation and Performance Monitoring | Supplier Evaluation |  |  | Display Supplier Evaluation by Time | Karmen/Chris/Jackson/Louie/Richard | Peter, Paul |  | Supplier Evaluation by Time (F1664) |  | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 5 |  | Daniel CK | Not Started |  |  | Daniel CK
QM | 1 | Sample Management | STS | Sample Management | Sample Management |  | 1 | Step 1 (to be specified after the solution configuration) | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful; LOUIE'S TEAM, (QC Chem) ACu Lam Aniqa Hasan, Christopher Moore | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 2. WIP | 2 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Sample Management | STS | Sample Management | Sample Management |  | 2 | Step 2 (to be specified after the solution configuration) | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful; LOUIE'S TEAM, (QC Chem) ACu Lam Aniqa Hasan, Christopher Moore | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 2. WIP | 2 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Sample Management | STS | Sample Management | Sample Management |  | 3 | Step 3 (to be specified after the solution configuration) | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful; LOUIE'S TEAM, (QC Chem) ACu Lam Aniqa Hasan, Christopher Moore | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 2. WIP | 2 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Sample Management | STS | Sample Management | Sample Management |  | 4 | Step 4 (to be specified after the solution configuration) | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful; LOUIE'S TEAM, (QC Chem) ACu Lam Aniqa Hasan, Christopher Moore | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 2. WIP | 2 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Sample Management | STS | Sample Management | Sample Management |  | 5 | Step 5 (to be specified after the solution configuration) | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful; LOUIE'S TEAM, (QC Chem) ACu Lam Aniqa Hasan, Christopher Moore | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 2. WIP | 2 |  | AlexC | Not Started |  |  | AlexC
QM | 1 | Sample Management | STS | Sample Management | Sample Management |  | 6 | Printing Sampling Labels | Kim, Ian, Devanshi, Marzena, Samriti, Zuber, Demetra, Chirag, Praful; LOUIE'S TEAM, (QC Chem) ACu Lam Aniqa Hasan, Christopher Moore | Demetra | TBD | TBD |  | SAP_BR_QUALITY_ENGINEER |  |  |  | 1. Not Started | 3 |  | AlexC | Not Started |  |  | AlexC
MM | 1 | Stock Transfer Order | 134 | Stock Transfer Order - intra-company | Stock Transfer Order |  |  | Create Outbound Delivery | Louie | Peter, Paul | VL10B | Create Outbound Delivery | createforPOInWebGUI | SAP_BR_SHIPPING_SPECIALIST |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2023-01-05 | Daniel CK | Scott, Karmen, Louie, Remo, Bana, Richard
MM | 1 | Stock Transfer Order | 134 | Stock Transfer Order - intra-company | Stock Transfer Order |  |  | Create Stock Transfer Order | Louie/Louie | Peter, Paul | ME21N | Create Stock Transfer Order | create | SAP_BR_PURCHASER |  |  |  | 3. Baseline Completed | 4 |  | Daniel CK | Completed |  | 2023-01-05 | Daniel CK | Scott, Karmen, Louie, Remo, Bana, Richard
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Reprocess Incoming Checks - From Lockbox | Eva | Milan, Jen | FEBA_LOCKBOX | Reprocess Incoming Checks - From Lockbox |  | SAP_BR_CASH_SPECIALIST_US |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2023-01-25 | Gil | Eva, Jen
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Upload Lockbox Files | Eva | Milan, Jen |  | Upload Lockbox Files |  | SAP_BR_CASH_SPECIALIST_US |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2023-01-25 | Gil | Eva, Jen
FI | 1 | Accounts Receivable | J59 | AR - Daily Processing | Daily Processing |  |  | Manage Lockbox Batches | Eva | Milan, Jen |  | Manage Lockbox Batches |  | SAP_BR_CASH_SPECIALIST_US |  |  |  | 3. Baseline Completed | 2 |  | Gil | Completed | 2022-12-09 | 2023-01-25 | Gil | Eva, Jen
<<< Insert above the line !! >>>

## Stats - Config
Sprint | (All)
Count of Config Status | Column Labels
Row Labels | 1. Not Started | 2. WIP | 3. Complete | Grand Total
FI | 51 |  |  | 51
MM | 1 |  |  | 1
QM | 29 | 5 |  | 34
SD |  | 8 |  | 8
WM |  | 1 |  | 1
Rebates |  | 8 | 1 | 9
Grand Total | 81 | 22 | 1 | 104
Sprint | (All)
Row Labels | Count of Config Status
(blank) | 1
BP maintenance | 1
(blank)
Sales Rebates
Not Started | 195
Accounts Payable | 6
Accounts Receivable | 7
Asset Accounting | 4
Bank Accounting & Cash Operations | 9
BP maintenance | 2
Credit Management | 4
Credits and Debits | 11
Customer Returns | 7
FI Month End | 17
General Ledger | 5
Inventory Accounting | 10
Inventory Management | 2
Inventory Reporting | 4
MM Master Data | 1
Overhead Cost Accounting | 9
Purchasing - Inventory | 2
Purchasing - Services | 1
Purchasing Reporting | 3
Quality Management in Procurement | 12
Quality Planning | 2
Sales Order Processing | 23
Sales Order Reporting | 15
Supplier Evaluation | 3
Production and Sell standard products | 12
Sales Rebates | 1
Make to Stock | 1
Quality Management in Discrete Manufacturing | 9
Quality Management in Stock Handling | 5
Quality Management with Trackwise | 2
Sample Management | 6
Cancelled | 20
Accounts Payable | 5
Asset Accounting | 5
Bank Accounting & Cash Operations | 2
Credit Management | 5
FI Month End | 3
On-Hold | 6
Accounts Receivable | 3
FI Month End | 2
General Ledger | 1
Completed | 224
Accounts Payable | 32
Accounts Receivable | 15
Asset Accounting | 27
Bank Accounting & Cash Operations | 10
Consumable Purchasing | 1
Credit Management | 2
Credits and Debits | 8
Customer Returns | 1
FI Month End | 15
General Ledger | 30
Inventory Accounting | 1
Inventory Management | 17
Material Master | 3
MM Master Data | 9
Overhead Cost Accounting | 8
Profitability and Cost Analysis | 1
Purchasing - Inventory | 2
Purchasing - Subcontracting | 6
Purchasing - Supplier Returns | 1
Sales Order Processing | 4
Sales Order Reporting | 8
Stock Transfer Order | 3
Production and Sell standard products | 8
Sales Rebates | 1
Material Requirements Planning | 4
Make to Stock | 4
Production Planning Analytics | 3
WIP | 29
Production Planning Master Data | 6
Quality Planning | 11
Production and Sell standard products | 1
Material Requirements Planning | 1
Make to Stock | 8
Production Planning Analytics | 2
Complete | 9
Sales Rebates | 9
Grand Total | 484

## Stats - BB
Count of Stream | Column Labels
Row Labels | DM | FI | MM | MM - ESM | PM | PP | PS | PS/CPM | QM | SD | SM | Grand Total
Accounts Payable |  | 3 | [9 empty] | 3
Accounts Receivable |  | 1 | [9 empty] | 1
Asset Accounting |  | 6 | [9 empty] | 6
Bank Accounting & Cash Operations |  | 8 | [9 empty] | 8
billing | [9 empty] | 1 |  | 1
BP maintenance | [9 empty] | 1 |  | 1
Build to Print | [6 empty] | 1 |  |  | 1 |  | 2
Consumable Purchasing |  |  | 1 | [8 empty] | 1
Contracts | [9 empty] | 1 |  | 1
Corrective Maintenance |  |  |  |  | 1 | [6 empty] | 1
Credit Management |  | 1 | [9 empty] | 1
Credits and Debits | [9 empty] | 5 |  | 5
Customer Returns | [9 empty] | 2 |  | 2
Document Management | 1 | [10 empty] | 1
Emergency Maintenance |  |  |  |  | 1 | [6 empty] | 1
Engineering Change Management | [5 empty] | 2 | [5 empty] | 2
Engineer-to-Order | [5 empty] | 1 | [5 empty] | 1
FI Month End |  | 8 | [9 empty] | 8
General Ledger |  | 6 | [9 empty] | 6
Inventory Accounting |  | 3 | [9 empty] | 3
Inventory Management |  |  | 4 | [8 empty] | 4
Inventory Reporting |  |  | 1 | [8 empty] | 1
Material Master |  |  | 3 | [8 empty] | 3
MM Master Data |  |  | 1 | [8 empty] | 1
Overhead Cost Accounting |  | 3 | [9 empty] | 3
Preventative Maintenance |  |  |  |  | 1 | [6 empty] | 1
Production Capacity Planning | [5 empty] | 2 | [5 empty] | 2
Production Order Processing | [5 empty] | 1 | [5 empty] | 1
Production Planning Master Data | [5 empty] | 6 | [5 empty] | 6
Production Rework Processing | [5 empty] | 2 | [5 empty] | 2
Profitability and Cost Analysis |  | 1 | [9 empty] | 1
Project Execution | [6 empty] | 1 |  |  |  |  | 1
Project Setup | [6 empty] | 1 | 1 |  |  |  | 2
Proposal and Cost Estimation | [7 empty] | 1 |  |  |  | 1
Purchasing - Inventory |  |  | 3 | [8 empty] | 3
Purchasing - Services |  |  |  | 1 | [7 empty] | 1
Purchasing - Subcontracting |  |  | 2 | [8 empty] | 2
Purchasing - Supplier Returns |  |  | 1 | [8 empty] | 1
Purchasing Reporting |  |  | 2 | [8 empty] | 2
Quality Management – Nonconformance Management | [8 empty] | 4 |  |  | 4
Quality Management - Production | [8 empty] | 2 |  |  | 2
Quality Management - Purchasing | [8 empty] | 3 |  |  | 3
Quality Management - Sales | [8 empty] | 2 |  |  | 2
Quotations | [9 empty] | 1 |  | 1
Request for Quotation |  |  | 1 | [8 empty] | 1
Research and Development | [5 empty] | 1 | [5 empty] | 1
Revenue Accounting and Reporting |  | 1 | [9 empty] | 1
Sales Order Processing | [9 empty] | 4 |  | 4
Sales Order Reporting | [9 empty] | 2 |  | 2
Service Management | [10 empty] | 1 | 1
Shipping | [9 empty] | 1 |  | 1
Stock Transfer Order |  |  | 1 | [8 empty] | 1
Supplier Evaluation |  |  | 1 | [8 empty] | 1
Grand Total | 1 | 41 | 21 | 1 | 3 | 15 | 3 | 2 | 11 | 19 | 1 | 118
Est Effort by Stream (3 hours / BB) | 3 | 123 | 63 | 3 | 9 | 45 | 9 | 6 | 33 | 57 | 3
Days of effort | 0.4 | 16.4 | 8.4 | 0.4 | 1.2 | 6 | 1.2 | 0.8 | 4.4 | 7.6 | 0.4 | 47.2
Est Effort by Step instead of by BB

## List of SOW BBs
BB | Description | Stream | Notes | Build Plan | Sprint
18J | Requisitioning | MM
1BM | Make-to-Order Production - Semifinished Goods Planning and Assembly | PP
1EG | Bank Integration with File Interface | FI |  |  | 4
1FM | Quality Management in Procurement | QM
1FS | Basic Warehouse Inbound Processing from Supplier | MM | Whs AUTO
1FU | Initial Stock Upload for Warehouse | MM | Whs AUTO
1FW | Physical Inventory in Warehouse | MM | Whs AUTO
1FY | Replenishment in Warehouse | MM | Whs AUTO
1G0 | Scrapping in Warehouse | MM | Whs AUTO
1G2 | Basic Warehouse Outbound Processing to Customer | MM | Whs AUTO
1I9 | Master Data Catalog for SAP S/4HANA - On-premise | ALL |  |  | n/a
1JI | Real-Time Reporting and Monitoring for Procurement | MM
1MI | Delivery Processing without Order Reference | SD
1MR | Quality Management in Stock Handling | QM
1V5 | Warehouse Inbound Processing from Supplier with Batch Management | MM | Whs AUTO
1V7 | Batch Management in Outbound Processing | MM | Whs AUTO
1V9 | Basic Warehouse Inbound Processing from Supplier with Quality Management | QM
1VB | Production Integration - Component Consumption and Receipt in Warehouse | PP
1XF | Request for Price | ???
22Z | Procurement of Services | MM
2FM | Financial Planning and Analysis | FI
2LN | Basic Available-to-Promise Processing | ???
2QU | Analytics - Purchase Order Visibility and Procurement Spend | MM
2QY | SAP Fiori Analytical Apps for Asset Accounting in Finance | FI
2V0 | SAP Fiori Analytical Apps for Quality Management | QM
3LO | Change Manufacturing Bill of Material for Production | PP
4B4 | Material Replenishment with Kanban - Stock Transfer | PP
4OZ | Planning of External Transportation Requirements | ???
1RI | Preferred Supplier List | MM
BD6 | Basic Credit Management | FI | include finance |  | 2
BD9 | Sell from Stock | SD
BDA | Free of Charge Delivery | SD
BDG | Sales Quotation | SD
BEG | Standard Cost Calculation | FI |  |  | 2
BFA | Basic Bank Account Management | FI |  | X | 1
BFB | Basic Cash Operations | FI
BGC | SAP Fiori Analytical Apps for G/L Accounting in Finance | FI
BGG | SAP Fiori Analytical Apps for Inventory and Warehouse Management | MM
BKA | Free Goods Processing | SD
BKN | Order-to-Cash Performance Monitoring | SD
BKP | Accelerated Customer Returns | SD
BLF | Batch Management | MM | include PP/QM
BLL | Serial Number Management | MM | include PP/QM
BMC | Core Inventory Management | MM
BMD | Purchase Contract | MM
BMY | Subcontracting | PP | include PP/QM
I9I | Sales Contract Management | SD
J45 | Procurement of Direct Materials | MM | include QM
J54 | Overhead Cost Accounting | FI | not in SOW! |  | 2
J58 | Accounting and Financial Close | FI |  |  | 3
J59 | Accounts Receivable | FI | include SD |  | 2
J60 | Accounts Payable | FI | include MM | X | 1
J62 | Asset Accounting | FI |  |  | 3
iPi | Rebates | SD | include finance
J56 | Enterprise Structure | ALL | not in SOW! | X | 1
1GA | Accounting and Financial Close - Group Ledger IFRS | FI | not in SOW! | X | 1
>>> | <<insert above the line>> | <<<

## SteriMax User Mapping
F | Account | F1 | F2 | ZS_ALL_USERS | Z_FLP_USER | ZS_SUPPORT_DISP | ZS_MM_PO_CREATOR | ZS_MM_PO_APPROVER | ZS_FI_AP_ACCOUNTANT | ZS_FI_AP_MANAGER | ZS_FI_AP_ACCOUNTANT_PROCUREMT | ZS_FI_AA_ACCOUNTANT | ZS_FI_AR_ACCOUNTANT | ZS_FI_CASH_SPECIALIST | ZS_FI_GL_ACCOUNTANT | ZS_FI_OVERHEAD_ACCOUNTANT | ZS_FI_CASH_MANAGER | ZS_FI_PRODN_ACCOUNTANT | ZS_FI_APR_ACCOUNTANT_FICA | ZS_FI_INVENTORY_ACCOUNTANT | ZS_FI_CREDIT_CONTROLLER | ZS_FI_BPC_EXPERT | ZS_FI_DIVISION_ACCOUNTANT | ZS_FI_AR_MANAGER | ZS_MM_PURCHASER | ZS_MM_INVENTORY_MANAGER | ZS_MM_MANAGER | ZS_MM_PRODMASTER_SPECIALIST | ZS_PP_PRODN_SUPERVISOR_DISC | ZS_PP_PRODN_ENG_PROC | ZS_PP_PRODN_PLNR | ZS_PP_PRODN_SUPERVISOR_PROC | ZS_QM_QUALITY_TECHNICIAN | ZS_QM_QUALITY_ENGINEER | ZS_RC_I4G01_SMARTBASEROLE | ZS_RC_I4G01_SMARTREBATEROLE | ZS_RC_I4G01_SMARTBILLBACKSROLE | ZS_SD_BUPA_MASTER_SPECIALIST | ZS_SD_SHIPPING_SPECIALIST | ZS_SD_INTERNAL_SALES_REP | ZS_SD_BILLING_CLERK | ZS_SD_RETURNS_REFUND_CLERK | ZS_SD_SALES_MANAGER | ZS_WM_WAREHOUSE_CLERK | ZS_WM_WAREHOUSE_CLERK_EWM | ZS_WM_WAREHOUSE_OPERATIVE_EWM | ZS_WM_RECEIVING_SPECIALIST | ZS_QM_QUALITY_PLANNER | ZS_QM_QUALITY_MANAGER | ZS_PP_DEVELOPMENT_MANAGER_DIN | ZS_SD_PRICING_SPECIALIST | ??? | ZS_FI_SALES_ACCOUNT | SAP_BR_CASH_SPECIALIST_US | SAP_BR_MATL_PLNR_EXT_PROC | ZS_PROJECT_TEAM
| ABORUDE |  |  | x | x | x | x
| ABOULIERIS |  |  | x | x | x | x | [20 empty] | x | [19 empty] | x
| ADALAL |  |  | x | x | x
| AFERNANDEZ |  |  | x | x | x | [18 empty] | x | x |  | x |  | x | x | x | [5 empty] | x | x | x |  |  | x | x | x
| AGUNAWAN |  |  | x | x | x | [8 empty] | x | x |  | x |  |  |  |  | x |  | x | [17 empty] | x | [9 empty] | x
| AHASAN |  |  | x | x | x | x | [25 empty] | x | [10 empty] | x | x
| AKAUR |  |  | x | x | x | x
| ALAM |  |  | x | x | x | [26 empty] | x | [10 empty] | x | x
| BBRKIC |  |  | x | x | x | [31 empty] | x | x | x | x | x | x | [7 empty] | x
| BKHANNA |  |  | x | x | x | x
| BPOLEKSIC |  |  | x | x | x | [21 empty] | x | [19 empty] | x
| CBAPOOJI |  |  | x | x | x | [31 empty] | x | x | x | x | x | x | [7 empty] | x
| CCHIU |  |  | x | x | x | x |  |  |  | x | x |  | x | x | x | x | x |  | x |  |  | x |  | x |  |  | x | x | [5 empty] | x | x | x | [5 empty] | x
| CDUMLAO |  |  | x | x | x | [8 empty] | x | x |  | x |  |  |  |  | x |  | x | [17 empty] | x | [9 empty] | x
| CMOORE |  |  | x | x | x | x | [25 empty] | x | [10 empty] | x | x
| CPATEL |  |  | x | x | x | [26 empty] | x | x | [9 empty] | x | x | x | x
| CPOTVIN |  |  | x | x | x |  | x
| CROCH |  |  | x | x | x | x
| CWOOD |  |  | x | x | x | x | [36 empty] | x
| CZHOU |  |  | x | x | x | x | [17 empty] | x | x |  | x |  | x | x | x | [5 empty] | x | [5 empty] | x | x
| DDESAI |  |  | x | x | x | [26 empty] | x | x | [9 empty] | x
| DMARAGOS |  |  | x | x | x |  | x | [19 empty] | x |  |  |  |  | x | x | [9 empty] | x |  |  |  | x | x
| DPATEL |  |  | x | x | x | [37 empty] | x
| DPUPOVAC |  |  | x | x | x |  | x
| DRAMSAMUJH |  |  | x | x | x | x
| DROTIM |  |  | x | x | x | x
| DYU |  |  | x | x | x | x | [36 empty] | x | x | x | x
| DZHU |  |  | x | x | x | x
| EDU |  |  | x | x | x | [37 empty] | x
| EHALFON |  |  | x | x | x
| EMORRISON |  |  | x | x | x |  | x
| ERAJASINGHAM |  |  | x | x | x |  | x
| ESEDLAK |  |  | x | x | x | x |  |  |  | x | x | x | x | x | x | x |  |  |  | x |  | x | x | [13 empty] | x |  | x | x | x | x | [7 empty] | x |  |  | x |  | x
| ESIDON |  |  | x | x | x | [37 empty] | x | x | x | x
| EZHANG |  |  | x | x | x |  | x
| FNADEAU |  |  | x | x | x |  | x
| GKHALID |  |  | x | x | x |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x
| GOSEI |  |  | x | x | x | [31 empty] | x | x | x | x | x | x | [7 empty] | x
| GPINTO |  |  | x | x | x | x
| HAHMAD |  |  | x | x | x |  |  | x |  | x | [13 empty] | x | [18 empty] | x
| HBARIAR |  |  | x | x | x | x
| HHEWITT |  |  | x | x | x | x
| HPATEL |  |  | x | x | x |  | x
| IJARVIS |  |  | x | x | x | [21 empty] | x |  |  |  |  | x | x | [9 empty] | x |  |  |  | x
| ILIS |  |  | x | x | x |  | x
| ISERAFIM |  |  | x | x | x | [26 empty] | x | [10 empty] | x | x
| JCHUI |  |  | x | x | x | x
| JJOHNSON |  |  | x | x | x |  | x
| JKANSARA |  |  | x | x | x | x
| JLEUNG |  |  | x | x | x | x |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  |  | x | [5 empty] | x | x | x | x |  | x | x | x | x | x | [8 empty] | X | x |  | x
| JMINIACI |  |  | x | x | x |  | x
| JPAQUETTE |  |  | x | x | x |  | x
| JPATEL |  |  | x | x | x | [37 empty] | x | x
| JPUNIA |  |  | x | x | x | x
| JREKHI |  |  | x | x | x | x |  | x | x | x | x |  |  | x | x |  | x | x |  |  |  | x |  | x | [12 empty] | x | [5 empty] | x
| JROBICHAUD |  |  | x | x | x |  | x
| JSOLTESZ |  |  | x | x | x |  | x
| JWAN |  |  | x | x | x | x
| JWANG |  |  | x | x | x | [8 empty] | x | x | [11 empty] | x | [6 empty] | x | x | x | x |  | x | x |  | x | [9 empty] | x
| JYIP |  |  | x | x | x | x | [17 empty] | x | x |  | x |  | x | x | x | [5 empty] | x |  |  |  |  | x | x | x
| KAMAN |  |  | x | x | x | x
| KDAI |  |  | x | x | x | [33 empty] | x
| KHO |  |  | x | x | x | x | [17 empty] | x | x |  | x |  | x | x | x | [5 empty] | x | x | x |  |  | x | x | x
| KMIDDLETON |  |  | x | x | x |  | x | [31 empty] | x |  |  | x
| KPUGSLEY |  |  | x | x | x | [21 empty] | x |  |  |  |  | x | x | [9 empty] | x |  |  |  | x
| KSIDHU |  |  | x | x | x | [37 empty] | x | x | x | x
| KSHAMSI |  |  | x | x | x | x
| LBERNSTEIN |  |  | x | x | x |  | x
| LCORONA |  |  | x | x | x | x
| LTEIXEIRA |  |  | x | x | x |  | x | [16 empty] | x | x |  | x |  | x | x | x | [5 empty] | x | x |  | x |  | x | x | x | x | x
| MBERRY |  |  | x | x | x | x
| MDUBOIS |  |  | x | x | x |  | x
| MGNATEK |  |  | x | x | x | [26 empty] | x | x | [9 empty] | x
| MKAUR |  |  | x | x | x
| MKERRISON |  |  | x | x | x
| MLOBE |  |  | x | x | x |  | x | [18 empty] | x
| MMARJANOVICH |  |  | x | x | x | x |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |  |  | x | x | [5 empty] | x | x | x | x |  | x | x | x | x | x | [8 empty] | x | x |  | x
| MNIAN |  |  | x | x | x |  | x
| MPETERS |  |  | x | x | x | x
| MRILEY |  |  | x | x | x |  | x | [35 empty] | x
| MTHAKUR |  |  | x | x | x | x
| MWINTER |  |  | x | x | x | x
| NBOOKER |  |  | x | x | x | [36 empty] | x | [9 empty] | x
| NSAAB |  |  | x | x | x | [37 empty] | x | x | x | x
| NSEHGAL |  |  | x | x | x |  | x
| NOBYRNE |  |  | x | x | x | [37 empty] | x | x | x | x
| NYOUNUS |  |  | x | x | x
| OEHANAH |  |  | x | x | x | x
| PDAVIDSON |  |  | x | x | x |  | x | [16 empty] | x | x | x | x |  | x | x | x | [5 empty] | x | x |  |  |  |  | x | x | x | x
| PMCCLURE |  |  | x | x | x
| PPANGAN |  |  | x | x | x
| PSTOCK |  |  | x | x | x |  | x | [16 empty] | x | x | x | x |  | x | x | x | [5 empty] | x | x |  |  |  |  | x | x | x | x
| RACHARYA |  |  | x | x | x |  | x
| RBONEY |  |  | x | x | x | x
| RDESTEBAN |  |  | x | x | x | [21 empty] | x | [19 empty] | x
| RDIMAULO |  |  | x | x | x
| RFERRONE |  |  | x | x | x | [19 empty] | x |  | x | [9 empty] | x |  | x | x |  | x | [7 empty] | x
| RGANDHI |  |  | x | x | x | x
| RGRASLEY |  |  | x | x | x | [37 empty] | x | x | x | x
| RGRASSI |  |  | x | x | x | x | [17 empty] | x | x | [17 empty] | x | x
| RPATEL |  |  | x | x | x | [21 empty] | x | [19 empty] | x
| RRAVAL |  |  | x | x | x | x
| RWILLIAMS |  |  | x | x | x |  | x
| RYOUNUS |  |  | x | x | x | [21 empty] | x | [19 empty] | x
| SACHARYA |  |  | x | x | x |  | x
| SAKOLKAR |  |  | x | x | x | x
| SALLEY |  |  | x | x | x | x | [17 empty] | x | x |  | x |  | x | x | x | [5 empty] | x | x | x |  |  | x | x | x | [9 empty] | x
| SKESHWANI |  |  | x | x | x | x
| SMAGHAM |  |  | x | x | x | x | [25 empty] | x | [10 empty] | x | x
| SMCBRIEN |  |  | x | x | x | x
| SMITCHELL |  |  | x | x | x |  | x | [29 empty] | x | x | x | x | x | x | [7 empty] | x
| SNIEWLAND |  |  | x | x | x |  | x | x | x |  |  |  | x | x | x | [6 empty] | x | x | [18 empty] | x
| SSHAH |  |  | x | x | x | x
| SSHARMA |  |  | x | x | x | [26 empty] | x | x | [9 empty] | x
| SWONG |  |  | x | x | x
| TBEGLEY |  |  | x | x | x | x
| TMORIN |  |  | x | x | x | x
| VILIC |  |  | x | x | x | x
| VKUNDALE |  |  | x | x | x | x
| WJEFFERY |  |  | x | x | x | x
| WKWAN |  |  | x | x | x |  |  | x | x | x | x | x | x | x | x | x | x |  | x | x | x | x | x | x |  |  | x | [6 empty] | x | x | x | x |  |  |  |  | x | [9 empty] | X
| WLUONG |  |  | x | x | x | x
| ZPATEL |  |  | x | x | x | x | [20 empty] | x |  |  |  |  | x | x | [9 empty] | x | x | x | x | x

## Role Mapping
Rank
Z_FLP_USER | Self Service
ZS_SUPPORT_DISP | Self Service
ZS_MM_PO_CREATOR | Advanced
ZS_MM_PO_APPROVER | Self Service
ZS_FI_AP_ACCOUNTANT | Advanced
ZS_FI_AP_MANAGER | Advanced
ZS_FI_AP_ACCOUNTANT_PROCUREMT | Advanced
ZS_FI_AA_ACCOUNTANT | Advanced
ZS_FI_AR_ACCOUNTANT | Advanced
ZS_FI_CASH_SPECIALIST | Advanced
ZS_FI_GL_ACCOUNTANT | Advanced
ZS_FI_OVERHEAD_ACCOUNTANT | Advanced
ZS_FI_CASH_MANAGER | Advanced
ZS_FI_PRODN_ACCOUNTANT | Advanced
ZS_FI_APR_ACCOUNTANT_FICA | Advanced
ZS_FI_INVENTORY_ACCOUNTANT | Advanced
ZS_FI_DIVISION_ACCOUNTANT | Advanced
ZS_FI_AR_MANAGER | Advanced
ZS_MM_PURCHASER | Advanced
ZS_MM_INVENTORY_MANAGER | Core
ZS_MM_MANAGER | Self Service
ZS_MM_PRODMASTER_SPECIALIST | Core Use
ZS_PP_PRODN_SUPERVISOR_DISC | Core Use
ZS_PP_PRODN_ENG_PROC | Core Use
ZS_PP_PRODN_PLNR | Core Use
ZS_PP_PRODN_SUPERVISOR_PROC | Core Use
ZS_QM_QUALITY_TECHNICIAN | Core Use
ZS_QM_QUALITY_ENGINEER | Core Use
ZS_RC_I4G01_SMARTBASEROLE | Self Service
ZS_RC_I4G01_SMARTREBATEROLE | Self Service
ZS_RC_I4G01_SMARTBILLBACKSROLE | Self Service
ZS_SD_BUPA_MASTER_SPECIALIST | Advanced
ZS_SD_SHIPPING_SPECIALIST | Core Use
ZS_SD_INTERNAL_SALES_REP | Core Use
ZS_SD_BILLING_CLERK | Advanced
ZS_SD_RETURNS_REFUND_CLERK | Advanced
ZS_SD_SALES_MANAGER | Advanced
ZS_WM_WAREHOUSE_CLERK | Self Service
ZS_WM_WAREHOUSE_CLERK_EWM | Self Service
ZS_WM_WAREHOUSE_OPERATIVE_EWM | Self Service
ZS_WM_RECEIVING_SPECIALIST | Self Service
ZS_QM_QUALITY_PLANNER | Core Use
ZS_QM_QUALITY_MANAGER | Core Use
ZS_PP_DEVELOPMENT_MANAGER_DIN | Core Use
ZS_SD_PRICING_SPECIALIST | Core Use
ZS_FI_SALES_ACCOUNT | Core Use
SAP_BR_CASH_SPECIALIST_US | Advanced
SAP_BR_MATL_PLNR_EXT_PROC | Core Use
ZS_PROJECT_TEAM | Advanced
ZS_FI_CREDIT_CONTROLLER | Core Use
ZS_FI_BPC_EXPERT | Core Use

## Role to Tcode Map
Stream | SAP Role Name | Custom Role Name | Role Name | FioriD | AppName | Custom Group | Notes | Roles
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/ADGI | Post Goods Issue - Unplanned | x |  | ZS_ALL_USERS
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/ADPROD | Create Warehouse Tasks - Product | x |  | Z_FLP_USER
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/CANCPICK | Cancel Picking | x |  | ZS_FI_AP_ACCOUNTANT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/DIFF_ANALYZER | Analyze Differences | x |  | ZS_FI_AP_MANAGER
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/LS01 | Create Storage Bins | x |  | ZS_FI_AP_ACCOUNTANT_PROCUREMT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/LS02 | Edit Storage Bins | x |  | ZS_FI_AA_ACCOUNTANT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/LS03 | Display Storage Bins | x |  | ZS_FI_AR_ACCOUNTANT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/LS11 | Mass Edit Storage Bins | x |  | ZS_FI_CASH_SPECIALIST
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/MON | Warehouse Monitor | x |  | ZS_FI_GL_ACCOUNTANT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/SBST | Sort Storage Bins | x |  | ZS_FI_OVERHEAD_ACCOUNTANT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/SBUP | Upload Storage Bins | x |  | ZS_FI_CASH_MANAGER
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/PI_COUNTLIST | Count Physical Inventory - List | x |  | ZS_FI_PRODN_ACCOUNTANT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/PI_CREATE | Create Physical Inventory - Documents | x |  | ZS_FI_APR_ACCOUNTANT_FICA
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/PI_PROCESS | Process Physical Inventory | x |  | ZS_FI_INVENTORY_ACCOUNTANT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/POST | Create Posting Changes | x |  | ZS_FI_CREDIT_CONTROLLER
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/PRDI | Maintain Inbound Deliveries | x |  | ZS_FI_BPC_EXPERT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/PRDO | Outbound Delivery Orders | x |  | ZS_FI_DIVISION_ACCOUNTANT
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/RSRC | Maintain Resources | x |  | ???
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | /SCWM/USER | Maintain User Settings - Radio Frequency | x |  | ZS_FI_AR_MANAGER
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | F1704 | Run Outbound Process - Deliveries | x |  | ZS_MM_PURCHASER
EWM | SAP_BR_WAREHOUSE_CLERK_EWM |  | Warehouse Clerk (Extended Warehouse Management) | F3340 | Count Physical Inventory | x |  | ZS_MM_INVENTORY_MANAGER
EWM | SAP_BR_WAREHOUSE_OPERATIVE_EWM |  | Warehouse Operative (Extended Warehouse Management) | /SCWM/RFUI | Test RF Environment | x |  | ZS_MM_MANAGER
EWM | SAP_BR_WAREHOUSE_OPERATIVE_EWM |  | Warehouse Operative (Extended Warehouse Management) | F3193 | Pack Outbound Deliveries | x |  | ZS_MM_PRODMASTER_SPECIALIST
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | AB08 | Reverse Journal Entry - Asset Accounting-Specific | X |  | ZS_PP_PRODN_SUPERVISOR_DISC
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | ABAVN | Post Retirement - By Scrapping | X |  | ZS_PP_PRODN_ENG_PROC
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | ABGFL | Post Credit Memo - After Year of Invoice | X |  | ZS_PP_PRODN_PLNR
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | ABGLL | Post Credit Memo - In Year of Invoice | X |  | ZS_PP_PRODN_SUPERVISOR_PROC
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | ABNAN | Post Post-Capitalization | X |  | ZS_QM_QUALITY_TECHNICIAN
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | ABUMN | Post Transfer - Within Company Code | X |  | ZS_QM_QUALITY_ENGINEER
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | ABZOL | Post Acquisition (Non-Integrated) - With Automatic Offsetting Entry | X |  | ZS_RC_I4G01_SMARTBASEROLE
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | AS01 | Create Asset | X |  | ZS_RC_I4G01_SMARTREBATEROLE
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | AS02 | Change Asset | X |  | ZS_RC_I4G01_SMARTBILLBACKSROLE
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | AS03 | Display Asset | X |  | ZS_SD_BUPA_MASTER_SPECIALIST
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | AW01N | Asset Values | X |  | ZS_SD_SHIPPING_SPECIALIST
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F-90 | Post Acquisition (Integrated AP) - Without Purchase Order | X |  | ZS_SD_INTERNAL_SALES_REP
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F1592 | Asset Master Worklist | X |  | ZS_SD_BILLING_CLERK
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F1614 | Asset Transactions | X |  | ZS_SD_RETURNS_REFUND_CLERK
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F1615A | Asset History Sheet (Design Studio) | X |  | ZS_SD_SALES_MANAGER
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F1616 | Depreciation Lists | X |  | ZS_WM_WAREHOUSE_CLERK
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F1617A | Asset Balances (Design Studio) | X |  | ZS_WM_WAREHOUSE_CLERK_EWM
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F1684 | Manage Fixed Assets | X |  | ZS_WM_WAREHOUSE_OPERATIVE_EWM
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F1914 | Schedule Asset Accounting Jobs | X |  | ZS_WM_RECEIVING_SPECIALIST
FI | SAP_BR_AA_ACCOUNTANT |  | Asset Accountant | F3096 | Asset Accounting Overview | X |  | ZS_QM_QUALITY_PLANNER
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F0701 | Display Supplier Balances | X |  | ZS_QM_QUALITY_MANAGER
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F0712 | Manage Supplier Line Items | X |  | ZS_PP_DEVELOPMENT_MANAGER_DIN
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F0770 | Manage Automatic Payments | X |  | ZS_PP_OTHERS
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F1367 | Clear Outgoing Payments | X |  | ZS_QM_OTHERS
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F1577 | Manage Checkbooks | X |  | ZS_PROJECT_TEAM
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F1578 | Manage Outgoing Checks | X
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F1688 | Manage Supplier Down Payment Requests | X
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F1861 | Display Supplier List | X
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F2388 | Monitor Payments | X
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | F2691 | Display Process Flow - Accounts Payable | X
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | FB60 | Create Incoming Invoices | X
FI | SAP_BR_AP_ACCOUNTANT |  | Accounts Payable Accountant | S_P99_41000099 | Display Payment Lists | X
FI | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  | Accounts Payable Accountant - Procurement | F1060A | Supplier Invoices List (Version 2) | X
FI | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  | Accounts Payable Accountant - Procurement | F2420 | Purchase Order Items by Account Assignment | X
FI | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  | Accounts Payable Accountant - Procurement | F2422 | Monitor Purchase Requisition Items By Account Assignment | X
FI | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  | Accounts Payable Accountant - Procurement | F2631 | Supplier Invoice Items by Account Assignment | X
FI | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  | Accounts Payable Accountant - Procurement | F2877 | Monitor Purchase Order Down Payments | X
FI | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  | Accounts Payable Accountant - Procurement | F3041 | Import Supplier Invoices | X
FI | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  | Accounts Payable Accountant - Procurement | MIRO | Create Supplier Invoice - Advanced | X
FI | SAP_BR_AP_ACCOUNTANT_PROCUREMT |  | Accounts Payable Accountant - Procurement | MRBR | Release Blocked Invoices | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1733 | Aging Analysis (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1735 | Cash Discount Forecast (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1736 | Cash Discount Utilization (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1740 | Days Payable Outstanding Analysis (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1743 | Future Payables (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1745 | Invoice Processing Analysis (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1746 | Overdue Payables (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1749 | Supplier Payment Analysis (Manual and Automatic Payments) (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F1750 | Supplier Payment Analysis(Open Payments) (S/4HANA) | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F2688 | Days Payable Outstanding - Detailed Analysis | X
FI | SAP_BR_AP_MANAGER |  | Accounts Payable Manager | F2917 | Accounts Payable Overview | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F0106A | Process Receivables (Version 2) | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F0703 | Display Customer Balances | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F0711 | Manage Customer Line Items | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F0744A | Create Correspondence (Version 2) | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F0773 | Clear Incoming Payments | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F1345 | Post Incoming Payments | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | Z* | FI Upload Payment | X | (currently in Sterimax FI group)
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F1520 | Reprocess Bank Statement Items | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F1689 | Manage Customer Down Payment Requests | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F2640 | Display Customer List | X
FI | SAP_BR_AR_ACCOUNTANT |  | Accounts Receivable Accountant | F2692 | Display Process Flow - Accounts Receivable | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F1619 | Reprocessing Rate of Incoming Payments | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F1739 | Days Beyond Terms (S/4HANA) | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F1741 | Days Sales Outstanding (S/4HANA) | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F1744 | Future Receivables (S/4HANA) | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F1747 | Overdue Receivables (S/4HANA) | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F1748 | Total Receivables (S/4HANA) | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F2539 | Overdue Receivables by Risk Class | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F2687 | Days Sales Outstanding - Detailed Analysis | X
FI | SAP_BR_AR_MANAGER |  | Accounts Receivable Manager | F3242 | Accounts Receivable Overview | X
FI | SAP_BR_CASH_MANAGER |  | Cash Manager | F0673A | Approve Bank Payments (Version 2) | X
FI | SAP_BR_CASH_MANAGER |  | Cash Manager | F0741A | Liquidity Forecast Details (Design Studio) | X
FI | SAP_BR_CASH_MANAGER |  | Cash Manager | F1366A | Manage Bank Accounts | X
FI | SAP_BR_CASH_MANAGER |  | Cash Manager | F1372 | Maintain Payment Approver | X
FI | SAP_BR_CASH_MANAGER |  | Cash Manager | F1574 | Manage Banks | X
FI | SAP_BR_CASH_MANAGER |  | Cash Manager | F2332 | Cash Flow Analyzer | X
FI | SAP_BR_CASH_MANAGER |  | Cash Manager | W0125 | Liquidity Forecast Details - Overview | X
FI | SAP_BR_CASH_SPECIALIST |  | Cash Management Specialist | F1564 | Manage Bank Statements | X
FI | SAP_BR_CREDIT_CONTROLLER |  | Credit Controller | F1751 | Credit Limit Utilization (S/4HANA) | X
FI | SAP_BR_CREDIT_CONTROLLER |  | Credit Controller | F2541 | Analyze Credit Exposure | x
FI | SAP_BR_CREDIT_CONTROLLER |  | Credit Controller | F4596 | Manage Credit Accounts | x
FI | SAP_BR_CREDIT_CONTROLLER |  | Credit Controller | F4825 | Display Credit Account Data | x
FI | SAP_BR_CREDIT_CONTROLLER |  | Credit Controller | F4826 | Display Credit Exposure | x
FI | SAP_BR_CREDIT_CONTROLLER |  | Credit Controller | F5587 | Manage Documented Credit Decisions | x
FI | SAP_BR_CREDIT_CONTROLLER |  | Credit Controller | UKM_CASE | Manage Credit Cases | x
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | 1KE4 | Profit Center Assignment Monitor | X
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | F0764 | Manage Profit Center Groups | x
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | F0926A | Profit Centers - Plan/Actual (Design Studio) | X
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | F0932A | Profit Centers - Plan/Actual YTD (Design Studio) | X
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | F0938A | Profit Centers - Plan/Actual with Currency Translation (Design Studio) | X
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | F0944A | Profit Centers - Actuals (Design Studio) | X
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | F3516 | Manage Profit Centers (Version 2) | X
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | F3751 | Where-Used List - Profit Centers | X
FI | SAP_BR_DIVISION_ACCOUNTANT |  | Divisional Accountant | KE56 | Edit Company Code Assignment - Profit Centers | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0707 | Display G/L Account Balances | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0708 | Balance Sheet/Income Statement | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0717 | Manage Journal Entries | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0718 | Post General Journal Entries | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0731A | Manage G/L Account Master Data (Version 2) | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0763A | Manage Chart of Accounts | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0956 | Journal Entry Analyzer | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0956A | Journal Entry Analyzer (S/4HANA) - Design Studio | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0996 | Trial Balance | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0996A | Trial Balance (Design Studio) | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F0997 | Audit Journal | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F1579 | Clear G/L Accounts - Manual Clearing | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F1596 | Carry Forward Balances | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F1927 | Schedule General Ledger Jobs | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2217 | Display Line Items in General Ledger | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2218 | Display Line Item Entry | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2223 | Reset Cleared Items | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2293 | Manage Posting Periods | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2445 | General Ledger Overview | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2547 | Verify General Journal Entries | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2548 | Upload General Journal Entries | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2728 | Verify Journal Entries in General Ledger - For Processor (Inbox) | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F2767 | Trial Balance Comparison (Design Studio) | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F3084 | Balance Sheet/Income Statement - Multidimensional (Design Studio) | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F3302 | Reconcile GR/IR Accounts | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F3616 | Currency Exchange Rates | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F3664 | Display Journal Entries in T-Account View | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F3665 | Display Document Flow | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | F4683 | Balance Carryforward Status | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | FBD4 | Display Changes of Recurring Entry | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | S_ALR_87012308 | G/L Account Changes | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | W0097 | Trial Balance Comparison | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | W0161 | Balance Sheet / Income Statement - Multidimensional | X
FI | SAP_BR_GL_ACCOUNTANT |  | General Ledger Accountant | W0177 | Year-To-Date Balances | X
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | CK11N | Create Material Cost Estimates | X
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | CK13N | Display Material Cost Estimates | x
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | CK24 | Release Material Cost Estimates | x
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | CK40N | Edit Costing Runs | x
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | CK82 | Material Cost Estimates | x
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | F1440A | Material Inventory Values - Rounding Differences (Design Studio) | x
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | F1865 | Manage Costing Runs - Estimated Costs | x
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | F2680 | Manage Material Valuations | x
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | S_ALR_87013047 | Cost Component Comparison | x
FI | SAP_BR_INVENTORY_ACCOUNTANT |  | Cost Accountant - Inventory | S_ALR_87099932 | Costing Run Comparison | x
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | CMACA02 | Maintain Activity Cost Rates | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0928 | Cost Centers - Plan/Actual YTD | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0928A | Cost Centers - Plan/Actual YTD (Design Studio) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0929 | Internal Orders - Plan/Actual YTD | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0929A | Internal Orders - Plan/Actual YTD (Design Studio) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0934 | Cost Centers - Plan/Actual with Currency Translation | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0934A | Cost Centers - Plan/Actual with Currency Translation (Design Studio) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0935 | Internal Orders - Plan/Actual with Currency Translation | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0935A | Internal Orders - Plan/Actual with Currency Translation (Design Studio) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0940 | Cost Centers - Actuals | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0940A | Cost Centers - Actuals (Design Studio) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0941 | Internal Orders - Actuals | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0941A | Internal Orders - Actuals (Design Studio) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0948 | Internal Orders - Plan/Actual | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0948A | Internal Orders - Plan/Actual (Design Studio) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0949 | Cost Centers - Plan/Actual | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F0949A | Cost Centers - Plan/Actual (Design Studio) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F1022 | Manage Internal Order (Web) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F1604 | Manage Internal Orders | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F1604A | Manage Internal Orders (Version 2) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F1711 | Import Financial Plan Data | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F3016 | Commitments by Cost Center | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F3338 | Manage Allocations | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F3396 | Copy Financial Plan Data | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | F4568 | Run Settlement - Actual | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | KO8G | Run Actual Settlement - Internal Orders, Run Settlement - Orders - Actual (Collective) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | KO8GH | Run Actual Settlement - Internal Orders, Run Settlement - Orders - Actual (Collective) | X
FI | SAP_BR_OVERHEAD_ACCOUNTANT |  | Cost Accountant - Overhead | KP26 | Edit Prices for Activity Types - Cost Centers | X
FI | SAP_BR_PRODN_ACCOUNTANT |  | Cost Accountant - Production | CO88 | Settle Orders, Settle Orders - Optimized | x
FI | SAP_BR_PRODN_ACCOUNTANT |  | Cost Accountant - Production | CO88H | Settle Orders, Settle Orders - Optimized | x
FI | SAP_BR_PRODN_ACCOUNTANT |  | Cost Accountant - Production | F1780 | Production Cost Analysis | x
FI | SAP_BR_PRODN_ACCOUNTANT |  | Cost Accountant - Production | F3331 | Analyze Costs by Work Center/Operation | x
FI | SAP_BR_PRODN_ACCOUNTANT |  | Cost Accountant - Production | FCO_KKBC_ORD_WRAPPER | Analyze Order | x
FI | SAP_BR_PRODN_ACCOUNTANT |  | Cost Accountant - Production | KKS1 | Run Variance Calculation - Orders - By Lot | X
FI | SAP_BR_PRODN_ACCOUNTANT |  | Cost Accountant - Production | KKS2 | Run Variance Calculation - Order - Single | X
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | F0379A | Physical Inventory Document Overview | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | F1076 | Stock - Single Material | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | F1595 | Stock - Multiple Materials | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | F1956 | Inventory Turnover Analysis | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | F2137 | Slow or Non-Moving Materials | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | F2769 | Overview Inventory Management | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | F2899 | Dead Stock Analysis | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | F3197 | Create Physical Inventory Documents | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | MB52 | Display Warehouse Stock | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | MI07 | Post Physical Inventory Document | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | MI10 | Enter and Post PI Count w/o Document | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | MI11 | Request Physical Inventory Recount | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | MI20 | Process Physical Inventory Count Results | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | W0055 | Goods Movement Analysis | x
MM | SAP_BR_INVENTORY_MANAGER |  | Inventory Manager | MMBE | Display Stock Overview | x
MM | SAP_BR_PRODMASTER_SPECIALIST |  | Master Data Specialist - Product Data | MM01 | Create Material Master | x
MM | SAP_BR_PRODMASTER_SPECIALIST |  | Master Data Specialist - Product Data | MM02 | Change Material Master | x
MM | SAP_BR_PRODMASTER_SPECIALIST |  | Master Data Specialist - Product Data | MM03 | Display Material Master | x
MM | SAP_BR_PRODMASTER_SPECIALIST |  | Master Data Specialist - Product Data | F1813 | Maintain Bill of Material | x
MM | SAP_BR_PRODMASTER_SPECIALIST |  | Master Data Specialist - Product Data | BP | Maitain Business Partner | x
MM | SAP_BR_PURCHASER |  | Purchaser | F4798 | My Area of Responsibility | x
MM | SAP_BR_PURCHASER |  | Purchaser | F3445 | Maintain PIRs | x
MM | SAP_BR_PURCHASER |  | Purchaser | F2101A | Monitor Material Coverage | x
MM | SAP_BR_PURCHASER |  | Purchaser | VL10B | My purchase Orders due for delivery | x
MM | SAP_BR_PURCHASER |  | Purchaser | F0842A | Manage Purchase Orders (Version 2) | x
MM | SAP_BR_PURCHASER |  | Purchaser | F1048 | Process Purchase Requisitions | x
MM | SAP_BR_PURCHASER |  | Purchaser | F2229 | Manage Purchase Requisition Professional | x
MM | SAP_BR_PURCHASER |  | Purchaser | F2358 | Monitor Purchase Order Items | x
MM | SAP_BR_PURCHASER |  | Purchaser | ME11 | Create Purchasing Info Record | x
MM | SAP_BR_PURCHASER |  | Purchaser | ME12 | Change Purchasing Info Record | x
MM | SAP_BR_PURCHASER |  | Purchaser | ME13 | Display Purchasing Info Record | x
MM | SAP_BR_PURCHASER |  | Purchaser | ME1L | Display Purchasing Info Record by Supplier | x
MM | SAP_BR_PURCHASER |  | Purchaser | F1377 | Spend Variance | x
MM | SAP_BR_PURCHASER |  | Purchaser | F3791 | Purchase Order Changes | x
MM | SAP_BR_PURCHASER |  | Purchaser | F1660 | Purchasing Group Activities | x
MM | SAP_BR_PURCHASER |  | Purchaser | F0682 | Invoice Price Variance | x
MM | SAP_BR_PURCHASER |  | Purchaser | ME57 | Assign and Process Purchase Requisitions | x
MM | SAP_BR_PURCHASER |  | Purchaser | ZMMR010 | Delivery Metrics | x
MM | SAP_BR_PURCHASER |  | Purchaser | ME21N | Create Purchase Order Advanced | x
MM | SAP_BR_PURCHASER |  | Purchaser | ME22N | Change Purchase Order Advanced | x
MM | SAP_BR_PURCHASER |  | Purchaser | ME23N | Display Purchase Order Advanced | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | F1077 | Material Documents Overview | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | F0869A | Create Outbound Deliveries From Sales Orders | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MIGO | Post Goods Movement | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | F1705 | Create Inbound Deliveries | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | F1706 | Change Inbound Deliveries | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MB90 | Output from Goods Movements | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | SP01 | Output Controller | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MB51 | Display Material Document List | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | F0343 | Overdue Purchase Order Items | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | F2416 | Overview Inventory Processing | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MI05 | Change Inventory Count | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MI06 | Display Inventory Count | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MI04 | Enter Inventory Count | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MI02 | Change Physical Inventory Document | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MI03 | Display Physical Inventory Document | x
MM | SAP_BR_WAREHOUSE_CLERK |  | Warehouse Clerk | MI21 | Print Physical Inventory Document | x
PP | ? |  | Other | C203 | Display Master Recipe | X
PP | ? |  | Other | C223 | Manage Production Versions, Manage Production Versions - C223 | X
PP | ? |  | Other | COR3 | Display Process Order | X
PP | ? |  | Other | COR6N | Confirm Process Order Phase | X
PP | ? |  | Other | COR7 | Convert Planned Order - to Process Order | X
PP | ? |  | Other | COR8 | Convert Planned Orders - to Process Orders | X
PP | ? |  | Other | CORT | Display Process Order Confirmation | X
PP | ? |  | Other | CRC3 | Display Resource | X
PP | ? |  | Other | MD04 | Monitor Stock / Requirements List | X
PP | ? |  | Other | MD61 | Create PIRs | X
PP | ? |  | Other | MD62 | Change PIRs | X
PP | ? |  | Other | MD63 | Display PIRs | X
PP | SAP_BR_DEVELOPMENT_MANAGER_DIN |  | Development Manager - Discrete Industries | F2212 | Manage Change Masters | X
PP | SAP_BR_PRODN_ENG_PROC |  | Production Engineer - Process Manufacturing | C201 | Create Master Recipe | x
PP | SAP_BR_PRODN_ENG_PROC |  | Production Engineer - Process Manufacturing | C202 | Change Master Recipe | x
PP | SAP_BR_PRODN_ENG_PROC |  | Production Engineer - Process Manufacturing | CRC1 | Create Resource | x
PP | SAP_BR_PRODN_ENG_PROC |  | Production Engineer - Process Manufacturing | CRC2 | Change Resource | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F0246 | Monitor External Requirements | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F0247A | Monitor Material Coverage (Version 2) | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F0250 | Manage External Requirements | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F0251 | Manage Material Coverage | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F0263 | Monitor Internal Requirements | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F0266A | Monitor Production Orders or Process Orders (Version 2) | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F0270 | Manage Internal Requirements | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F0273 | Manage Production Orders or Process Orders | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2034 | Operation Scrap | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2035 | Material Scrap | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2171 | Excess Component Consumption | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2172 | Production Execution Duration | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2260 | Planned Order Object Page | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2261 | Production Order Object Page | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2262 | Work Center Object Page | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2263 | Process Order Object Page | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2264 | Resource Object Page | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F2900 | Monitor Capacity Utilization - Object Page | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F3289 | Manage Work Center Capacity | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F3853 | Detect MRP Situations | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F4170 | Manage Planned Orders | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F4171 | Convert Planned Orders | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F4796 | My Area of Responsibility - MRP Controller | x
PP | SAP_BR_PRODN_PLNR |  | Production Planner | F5447 | Schedule Unassigning of MRP Areas | x
PP | SAP_BR_PRODN_SUPERVISOR_DISC |  | Production Supervisor - Discrete Manufacturing | F2216 | Scrap Reasons | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | COHVPI | Mass Processing: Process Orders | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | COOISPI | Monitor Process / Planned Orders | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | COR1 | Create Process Order | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | COR2 | Change Process Order | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | COR5 | Release Process Orders | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | CORK | Confirm Process Order | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | CORO | Create Process Order w/o Material | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | F2266 | Process Order Confirmation Object Page | x
PP | SAP_BR_PRODN_SUPERVISOR_PROC |  | Production Supervisor - Process Manufacturing | F4587 | Manage Process Orders | x
QM | ? |  | Other | BMBC | Batch Information Cockpit | X
QM | ? |  | Other | QA01 | Create Inspection Lot | X
QM | ? |  | Other | QA02 | Change Inspection Lot | X |  | Market Segments
QM | ? |  | Other | QA03 | Display Inspection Lot | X
QM | ? |  | Other | QA13 | Display Usage Decision | X
QM | ? |  | Other | QA32 | Process Inspection Lots - Worklist | X
QM | ? |  | Other | QA33 | Display Inspection Lots - Worklist | X
QM | ? |  | Other | QDL3 | Display Quality Level | X
QM | ? |  | Other | QDP3 | Display Sampling Scheme | X
QM | ? |  | Other | QDV3 | Display Sampling Procedure | X
QM | ? |  | Other | QE01 | Record Inspection Results - For Operation | X
QM | ? |  | Other | QE02 | Change Inspection Results - For Operation | X
QM | ? |  | Other | QE03 | Display Inspection Results - For Operation | X
QM | ? |  | Other | QE06 | Display Inspection Results - For Inspection Sample | X
QM | ? |  | Other | QI01 | Create Quality Info Record - Procurement | X
QM | ? |  | Other | QI02 | Change Quality Info Record - Procurement | X
QM | ? |  | Other | QI03 | Display Quality Info Record - Procurement | X
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | F2256A | Manage Quality Info Records | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | F2345 | Manage Usage Decisions | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | F2360 | Quality Engineer Overview | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | F2914 | Manage Quality Levels | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | F3382 | Characteristic Detailed Analytics | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | F3383 | Characteristic Analytics | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QA11 | Record Usage Decision | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QA12 | Change Usage Decision | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QA14 | Change Usage Decision - Without History | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QAC1 | Change Inspection Lot - Actual Quantity | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QAC2 | Transfer Inspection Stock | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QAC3 | Cancel Sample Determination - For Inspection Lot | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QD33 | Delete Quality Level | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QDH1 | Change Quality Level Evaluation | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QDH2 | Display Quality Level Evaluation | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QDL1 | Create Quality Level | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QDL2 | Change Quality Level | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QK05 | Display Confirmed Activities - For Inspection Lot | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QST01 | Create Stability Study | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QST07 | Change Stability Study - Testing Schedule Items | x
QM | SAP_BR_QUALITY_ENGINEER |  | Quality Engineer | QST09 | Maintain Stability Study - Planning Building Block | x
QM | SAP_BR_QUALITY_MANAGER |  | Quality Manager | F3239 | Inspection Lot Analytics | X
QM | SAP_BR_QUALITY_MANAGER |  | Quality Manager | F3273 | Inspection Lot Detailed Analytics | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | CRQ1 | Create QM Work Center | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | CWBQM | Inspection Plans - Engineering Workbench | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | F2255 | Display Sampling Procedure | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | F2256 | Display Quality Info Record for Procurement | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | F3788 | Manage Inspection Plans | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDB1 | Sampling Procedure - Assign Dynamic Modification Rule | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDP1 | Create Sampling Scheme | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDP2 | Change Sampling Scheme | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDR1 | Create Dynamic Modification Rule | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDR2 | Change Dynamic Modification Rule | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDR7 | Dynamic Modification Rule - Replace Usage | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDV1 | Create Sampling Procedure | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDV2 | Change Sampling Procedure | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QDV7 | Sampling Procedure - Replace Usage | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QP01 | Create Inspection Plan | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QP02 | Change Inspection Plan | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QP06 | Display Inspection Plans - Missing or Unusable | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QP07 | Display Inspection Plans - Missing or Unusable in Procurement | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QP11 | Create Reference Operation Set | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QP12 | Change Reference Operation Set | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QP60 | Display Inspection Plan Changes | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QP61 | Inspection Plan - Display Change Documents | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QPV2 | Edit Sample-Drawing Procedure | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QS21 | Create Master Inspection Characteristic | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QS23 | Change Master Inspection Characteristic | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QS25 | Delete Master Inspection Characteristic | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QS27 | Replace Master Inspection Characteristic | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QS61 | Edit Material Specification | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QS63 | Edit Material Specification - For Key Date | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QS65 | Activate Material Specification | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QSR5 | Archive Inspection Plans | X
QM | SAP_BR_QUALITY_PLANNER |  | Quality Planner | QSR6 | Delete Inspection Plans | X
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F0309A | Display Inspection Points | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F1685A | Record Inspection Results | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F2180 | Inspection Lot (S/4HANA) | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F2181 | Inspection Operation (S/4HANA) | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F2219 | Display Master Inspection Characteristics | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F2254 | Display Samples | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F2343 | Manage Inspection Lots | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F2361 | Quality Technician Overview | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F2428 | Display Results History | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F2689 | Record Results for Inspection Points | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | F3365 | Record Inspection Results in Table Form | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | QPR1 | Create Sample | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | QPR2 | Change Sample | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | QPR4 | Process Sample Drawing | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | QPR6 | Create Sample - With Reference | x
QM | SAP_BR_QUALITY_TECHNICIAN |  | Quality Technician | QPR7 | Change Storage Data - For Sample | x
SD | SAP_BR_BILLING_CLERK |  | Billing Clerk | F0797 | Manage Billing Documents | x
SD | SAP_BR_BILLING_CLERK |  | Billing Clerk | F0798 | Create Billing Documents | x
SD | SAP_BR_BILLING_CLERK |  | Billing Clerk | F1510 | Schedule Billing Output | x
SD | SAP_BR_BILLING_CLERK |  | Billing Clerk | F1518 | Schedule Billing Release | x
SD | SAP_BR_BILLING_CLERK |  | Billing Clerk | F1519 | Schedule Billing Creation | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | BS_OVP_BP (BS_OVP_BP_ALL) | Change Business Partner (All Data) - Governance | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | F0046A | Customer Master FactSheets | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | F0850A | Manage Customer Master Data | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | F3163 | Manage Business Partner Master Data | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | F4752 | Monitor Open Work Items from Change Requests for Business Partners | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | FD09 | Confirm Customer List (Accounting) | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | FK09 | Confirm Supplier List (Accounting) | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | XD99 | Customer master mass maintenance | x
SD | SAP_BR_BUPA_MASTER_SPECIALIST |  | Master Data Specialist - Business Partner Data | XK99 | Mass maintenance, vendor master | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F0029A | Sales Order Fulfillment Issues (Version 2) | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F1814 | Sales Order (S/4HANA) | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F1846 | Credit Memo Request | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F1848 | Debit Memo Request | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F1873 | Manage Sales Orders | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F1988 | Manage Debit Memo Requests | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F1989 | Manage Credit Memo Requests | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2187 | Customer - 360Â° View | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2200 | My Sales Overview | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2430 | List Incomplete Sales Documents | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2459 | Schedule Sales Document Output | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2499 | Manage Customer Materials | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2577 | Track Sales Orders (S/4HANA) | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2583 | Manage Sales Item Proposals | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2713 | Manage Sales Documents with Customer-Expected Price | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F2981 | Track Sales Order Details | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F3245 | Manage Duplicate Sales Documents | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F3893 | Process Sales Orders | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F3894 | Assign Sold-to Parties | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F3895 | Manage Delivery Schedule Processing | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F4293 | Import Sales Orders | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F4645 | Customers Overview | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F4920 | Create Sales Orders - Automatic Extraction | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F5091 | Mass Change of Sales Documents | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F5211 | Mass Change of Sales Orders | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F5279 | Mass Change of Customer Returns | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F5280 | Mass Change of Debit Memo Requests | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | F5281 | Mass Change of Credit Memo Requests | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | VA51 | Create Sales Item Proposals | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | VA52 | Change Sales Item Proposals | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | VA53 | Display Item Proposal, Display Sales Item Proposals | x
SD | SAP_BR_INTERNAL_SALES_REP |  | Internal Sales Representative | VA55 | List Item Proposals | x
SD | SAP_BR_RETURNS_REFUND_CLERK |  | Returns & Refund Clerk | F1708 | Manage Customer Returns | x
SD | SAP_BR_RETURNS_REFUND_CLERK |  | Returns & Refund Clerk | F1815 | Customer Return | x
SD | SAP_BR_RETURNS_REFUND_CLERK |  | Returns & Refund Clerk | F2303 | Sales Order without Charge | x
SD | SAP_BR_RETURNS_REFUND_CLERK |  | Returns & Refund Clerk | F2305 | Manage Sales Orders without Charge | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F1249 | Incoming Sales Orders - Flexible Analysis | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F1250 | Sales Volume - Flexible Analysis | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F2235 | Sales Volume - Detailed Analysis | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F2270 | Sales Volume - Check Open Sales | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F2271 | Sales Volume - Profit Margin | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F2458 | Sales Order - Demand Fulfillment | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F2601 | Sales Management Overview | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F2783 | Delivery Performance - Delivered as Requested | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F3889 | Customer Returns - Flexible Analysis (Design Studio) | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | F4092 | Customer Returns - Return Rate | x
SD | SAP_BR_SALES_MANAGER |  | Sales Manager | W0139 | Customer Returns | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F0234A | Returns Delivery (S/4HANA) | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F0867A | Manage Outbound Deliveries | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F0868 | Pick Outbound Delivery | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F0869A | Create Outbound Deliveries - From Sales Orders | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F0870A | Analyze Delivery Logs | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F2228 | Schedule Delivery Creation | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F2259 | Schedule Goods Issue For Deliveries | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F2878A | Analyze Delivery Performance - Shipped as Planned | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F3487 | Create Delivery with Reference to Sales Order | x
SD | SAP_BR_SHIPPING_SPECIALIST |  | Shipping Specialist | F3488 | Create Delivery without a Reference (Quick Create) | x

## Lists
Status | Person Resp | Person Receive | Active/Cancelled | KT Status
1. Not Started | Gil |  | ACTIVE | Not Started
2. WIP | Ahmad |  | CANCELLED | WIP
3. Baseline Completed | James |  |  | Completed
4. Delta Completed/Unit Testing | Daniel CK |  |  | Cancelled
5. On Hold by NTT | Alex |  |  | On-Hold
7. QA Approved | Jessica
9. CANCELLED/Out Of Scope | Andzor
10. On Hold by Customer | Daniel G
Joska
Sireesha